## Cover
SAMPLE REAL ESTATE DEVELOPMENT
REPORTS ON PIPELINE

## List of Active Projects
PROJECT NAME | Developer | City | Number of Units | Construction Type | Development Stage | Population Served - Primary | EST TDC for Phase (in millions) | Est Gross Developer Fee | Management Company | Date of Close
Englewood Apartments | M Angelini | Chicago | 99 | New Construction | Operations - Sub Phase Close Out | Special Needs (PSH) | 16780500 | 360000 | MHMG | 2008-12-01
Countryside Senior Apts | L Reyes | Countryside | 70 | New Construction | Operations - Sub Phase Close Out | Senior | 16101522 | 1129550 | MHMG | 2009-09-01
Milwaukee - Johnston Center | D Lyon | Milwaukee | 91 | Adaptive/ Rehab | Operations - Sub Phase Close Out | Special Needs (PSH) | 13848000 | 1436566.7356 | MHMG | 2009-12-01
Roseland Place | L Reyes | Chicago | 60 | New Construction | Operations - Sub Phase Close Out | Senior | 17786000 | 700570 | MHMG | 2009-12-01
850 N Eastwood | M Angelini | Chicago | 231 | Acquisition/ Rehab | Operations - Sub Phase Lease Up | Family | 53000000 | 3000 | Leasing & Mgmt Corp. | 2010-08-01
Harold Washington Apts | M Angelini | Chicago | 69 | Refinance/ Rehab | Operations - Sub Phase Close Out | Special Needs (PSH) | 15100000 | 997000 | MHMG | 2010-08-01
Grayslake Senior | L Reyes | Grayslake | 70 | New Construction | Construction | Senior | 21400000 | 1522737 | MHMG | 2011-11-02
Pullman Wheelworks | L Brace | Chicago | 210 | Acquisition/ Rehab | Construction | Family | 30136151 | 1100000 | Leasing and Mgmt Corp. | 2011-12-01
Kankakee | L Reyes | Kankakee | 70 | New Construction | Development | Senior | 18900000 | 1256980 | MHMG | 2013-10-01
Sterling Park | M Angelini | Chicago | 181 | Adaptive/ Rehab | Development | Family | 45700000 | 1000000 | MHMG | 2012-11-01
15 Year Refi-Uptown Portfolio | M Angelini & A Blakley | Chicago | 449 | Refinance/ Rehab | Feasibility | Special Needs (PSH) | 43752605 | 1523500 | MHMG | 2012-12-01
26th & Kostner/Keating | L Brace | Chicago | 125 | Adaptive/ Rehab | Prospect | Family | 52200000 | 3882726.75 | MHMG | 2012-12-01
Danville VA Hospital Site | D Lyon | Danville | 65 | New Construction | Feasibility | Special Needs (PSH) | 20000000 | 1303125 | MHMG | 2012-12-01
Children's Memorial Site | M Angelini | Chicago | 95 | Adaptive/ Rehab | Prospect | Senior | 17500000 | 1312500 | MHMG | 2013-03-01
YMCA Austin | L Brace | Chicago | 160 | New Construction | Prospect | Special Needs (PSH) | 32000000 | 1000000 | MHMG | 2013-10-01
5th Ward Senior Project/ Milwaukee | D Lyon | Milwaukee | 55 | New Construction | Development | Senior | 9500000 | 666750 | MHMG | 2013-12-01
Johnston Center 2 | D Lyon | Milwaukee | 55 | New Construction | Prospect | Family | 9625000 | 675000 | MHMG | 2013-12-01
Milwaukee Greenwich Apartments | D Lyon | Milwaukee | 55 | New Construction | Development | Family | 11000000 | 789000 | MHMG | 2013-12-01
Westside Resyndication | A Blakley | Chicago | 315 | Refinance/ Rehab | Feasibility | Family | 30712500 | 999999.5 | MHMG | 2013-12-01
Menomonee River Valley | D Lyon | Milwaukee | 60 | New Construction | Prospect | Family | TBD | TBD | MHMG | 2014-12-01
Pullman Wheelworks, Phase 2 | M Angelini | Chicago | 60 | New Construction | Prospect | Senior | TBD | TBD | MHMG | 2014-12-01
Danville VA Hospital Site - Phase 2 | D Lyon | Danville | 65 | New Construction | Feasibility | Special Needs (PSH) | 20000000 | 1303125 | MHMG | 2014-12-01
MuskegonTrinity site | 0 | Muskegon, MI | 0 | Adaptive/ Rehab | Feasibility | Family | 0 | 0 | MHMG | 0
Mercy Housing/Ickes Site | 0 | Chicago | 0 | New Construction | Feasibility | Family | 0 | 0 | MHMG | 0
TOTALS |  |  | 2710 |  |  |  | 495042278 | 22962129.9856

## Pipeline Demographics-Active
Pipeline Demographics - ACTIVE Projects
PROJECT TYPE
Type of Project | No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
Special Needs (PSH) | 7 | 29.17% | 998 | 36.83% | 161481105 | 32.62%
Senior | 10 | 41.67% | 480 | 17.71% | 101187522 | 20.44%
SF For Sale | 0 | 0% | 0 | 0% | 0 | 0%
Family | 7 | 29.17% | 1232 | 45.46% | 232373651 | 46.94%
TOTALS | 24 | 100% | 2710 | 100% | 495042278 | 100%
PROJECTS BY GEOGRAPHIC AREA
Project Area | No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
Chicago | 14 | 58.33% | 2054 | 75.79% | 354667756 | 71.64%
Milwaukee | 5 | 20.83% | 316 | 11.66% | 43973000 | 8.883%
Countryside | 1 | 4.167% | 70 | 2.583% | 16101522 | 3.253%
Aurora | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Grayslake | 1 | 4.167% | 70 | 2.583% | 21400000 | 4.323%
Kankakee | 1 | 4.167% | 70 | 2.583% | 18900000 | 3.818%
Collar Counties | 3 | 12.5% | 210 | 7.749% | 56401522 | 11.39%
Danville | 2 | 8.333% | 130 | 4.797% | 40000000 | 8.08%
Indianapolis | 0 | 0% | 0 | 0% | 0 | 0%
St. Louis | 0 | 0% | 0 | 0% | 0 | 0%
Downstate/ Other States | 2 | 8.333% | 130 | 4.797% | 40000000 | 8.08%
TOTAL | 24 | 100% | 2710 | 100% | 495042278 | 100%
PROJECTS BY CONSTRUCTION TYPE
| No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
New Construction | 14 | 58.33% | 944 | 34.83% | 193093022 | 39.01%
Acquisition/ Rehab | 2 | 8.333% | 441 | 16.27% | 83136151 | 16.79%
Adaptive/ Rehab | 5 | 20.83% | 492 | 18.15% | 129248000 | 26.11%
Refinance/ Rehab | 3 | 12.5% | 833 | 30.74% | 89565105 | 18.09%
Rehab | 0 | 0% | 0 | 0% | 0 | 0%
TOTALS | 24 | 100% | 2710 | 100% | 495042278 | 100%
STAGES OF DEVELOPMENT BY PROJECT
Stage of Development | No. of Projects | % of Total | No of Units | % of Total | Total Develop. Costs | % of Total
Prospect | 6 | 25% | 555 | 20.48% | 111325000 | 22.49%
Feasibility | 6 | 25% | 894 | 32.99% | 114465105 | 23.12%
Development | 4 | 16.67% | 361 | 13.32% | 85100000 | 17.19%
Construction | 2 | 8.333% | 280 | 10.33% | 51536151 | 10.41%
Operations - Lease Up | 1 | 4.167% | 231 | 8.524% | 53000000 | 10.71%
Operations - Close Out | 5 | 20.83% | 389 | 14.35% | 79616022 | 16.08%
TOTALS | 24 | 100% | 2710 | 100% | 495042278 | 100%
SCHEDULE OF PROJECT CLOSINGS AND DEVELOPER FEES BY YEAR*
Year of Closing | Closings by Year | % of Total | No of Units | % of Total | Total Develop. Costs | Net Developer Fee**
2011 | 2 | 11.11% | 280 | 13.4% | 51536151 | 1404313
2012 | 4 | 22.22% | 820 | 39.23% | 161652605 | 2887333.8
2013 | 7 | 38.89% | 805 | 38.52% | 129237500 | 2997473.5
2014 | 3 | 16.67% | 185 | 8.852% | 20000000 | 5110925.875
2015 | 2 | 11.11% | 0 | 0% | 0 | 4959785.875
2016 | 0 | 0% | 0 | 0% | 0 | 2815393.75
TOTAL | 18 | 100% | 2090 | 100% | 362426256 | 20175225.8
*Does not include projects closed before 2011 or projects with TBD closing dates
**The net developer fee is for projects closing in that year and projects closed in previous years

## Pipeline Demographics-Inactive
Pipeline Demographics - INACTIVE Projects
PROJECT TYPE
Type of Project | No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
Special Needs (PSH) | 2 | 11.76% | 220 | 19.16% | 44100000 | 17.84%
Senior | 4 | 23.53% | 445 | 38.76% | 112522110 | 45.53%
Family | 7 | 41.18% | 375 | 32.67% | 68925000 | 27.89%
For Sale | 4 | 23.53% | 108 | 9.408% | 21600000 | 8.74%
TOTALS | 17 | 100% | 1148 | 100% | 247147110 | 100%
PROJECTS BY GEOGRAPHIC AREA
Project Area | No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
Chicago | 10 | 58.82% | 623 | 54.27% | 156425000 | 63.29%
Milwaukee | 0 | 0% | 0 | 0% | 0 | 0%
Countryside | 0 | 0% | 0 | 0% | 0 | 0%
Aurora | 4 | 23.53% | 355 | 30.92% | 83712560 | 33.87%
Grayslake | 0 | 0% | 0 | 0% | 0 | 0%
Kankakee | 0 | 0% | 0 | 0% | 0 | 0%
Collar Counties | 4 | 23.53% | 355 | 30.92% | 83712560 | 33.87%
Danville | 1 | 5.882% | 50 | 4.355% | 7009550 | 2.836%
Indianapolis | 1 | 5.882% | 60 | 5.226% | 0 | 0%
St. Louis | 1 | 5.882% | 60 | 5.226% | 0 | 0%
Downstate/ Other States | 3 | 17.65% | 170 | 14.81% | 7009550 | 2.836%
TOTAL | 17 | 100% | 1148 | 100% | 247147110 | 100%
PROJECTS BY CONSTRUCTION TYPE
| No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
New Construction | 15 | 88.24% | 893 | 77.79% | 193522110 | 78.3%
Acquisition/ Rehab | 2 | 11.76% | 255 | 22.21% | 53625000 | 21.7%
Adaptive/ Rehab | 0 | 0% | 0 | 0% | 0 | 0%
Refinance/ Rehab | 0 | 0% | 0 | 0% | 0 | 0%
Rehab | 0 | 0% | 0 | 0% | 0 | 0%
TOTALS | 17 | 100% | 1148 | 100% | 247147110 | 100%
STAGES OF DEVELOPMENT BY PROJECT
Stage of Development | No. of Projects | % of Total | No of Units | % of Total | Total Develop. Costs | % of Total
Prospect | 3 | 17.65% | 280 | 24.39% | 28800000 | 11.65%
Feasibility | 14 | 82.35% | 868 | 75.61% | 218347110 | 88.35%
Development | 0 | 0% | 0 | 0% | 0 | 0%
Construction | 0 | 0% | 0 | 0% | 0 | 0%
Operations - Lease Up | 0 | 0% | 0 | 0% | 0 | 0%
Operations - Close Out | 0 | 0% | 0 | 0% | 0 | 0%
TOTALS | 17 | 100% | 1148 | 100% | 247147110 | 100%
SCHEDULE OF PROJECT CLOSINGS AND DEVELOPER FEES BY YEAR*
Year of Closing | Closings by Year | % of Total | No of Units | % of Total | Total Develop. Costs | Net Developer Fee**
2011 | 0 | 0% | 0 | 0% | 0 | 0
2012 | 0 | 0% | 0 | 0% | 0 | 0
2013 | 3 | 21.43% | 315 | 29.89% | 93462560 | 1555379
2014 | 5 | 35.71% | 420 | 39.85% | 64100000 | 452983
2015 | 3 | 21.43% | 170 | 16.13% | 35809550 | 1995477
2016 | 3 | 21.43% | 149 | 14.14% | 34975000 | 3198665
2017 | 0 | 0% | 0 | 0% | 0 | 1647822
2018 | 0 | 0% | 0 | 0% | 0 | 1785701
TOTAL | 14 | 100% | 1054 | 100% | 228347110 | 10636027
*Does not include projects closed before 2011 or projects with TBD closing dates
**The net developer fee is for projects closing in that year and projects closed in previous years

## Pipeline Demographics-ALL
Pipeline Demographics - ALL Projects
PROJECT TYPE
Type of Project | No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
Special Needs (PSH) | 9 | 21.95% | 1218 | 31.57% | 205581105 | 27.7%
Senior | 14 | 34.15% | 925 | 23.98% | 213709632 | 28.79%
Family | 14 | 34.15% | 1607 | 41.65% | 301298651 | 40.6%
For Sale | 4 | 9.756% | 108 | 2.799% | 21600000 | 2.91%
TOTALS | 41 | 100% | 3858 | 100% | 742189388 | 100%
PROJECTS BY GEOGRAPHIC AREA
Project Area | No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
Chicago | 24 | 58.54% | 2677 | 69.39% | 511092756 | 68.86%
Milwaukee | 5 | 12.2% | 316 | 8.191% | 43973000 | 5.925%
Countryside | 1 | 2.439% | 70 | 1.814% | 16101522 | 2.169%
Grayslake | 1 | 2.439% | 70 | 1.814% | 21400000 | 2.883%
Aurora | 4 | 9.756% | 355 | 9.202% | 83712560 | 11.28%
Kankakee | 1 | 2.439% | 70 | 1.814% | 18900000 | 2.547%
Collar Counties | 7 | 17.07% | 565 | 14.64% | 140114082 | 18.88%
Danville | 3 | 7.317% | 180 | 4.666% | 47009550 | 6.334%
Indianapolis | 1 | 2.439% | 60 | 1.555% | 0 | 0%
St. Louis | 1 | 2.439% | 60 | 1.555% | 0 | 0%
Downstate/ Other States | 5 | 12.2% | 300 | 7.776% | 47009550 | 6.334%
TOTAL | 41 | 100% | 3858 | 100% | 742189388 | 100%
PROJECTS BY CONSTRUCTION TYPE
| No. of Projects | % of Total | No. of Units | % of Total | Total Develop. Costs | % of Total
New Construction | 29 | 70.73% | 1837 | 47.62% | 386615132 | 52.09%
Acquisition/ Rehab | 4 | 9.756% | 696 | 18.04% | 136761151 | 18.43%
Adaptive/ Rehab | 5 | 12.2% | 492 | 12.75% | 129248000 | 17.41%
Refinance/ Rehab | 3 | 7.317% | 833 | 21.59% | 89565105 | 12.07%
Rehab | 0 | 0% | 0 | 0% | 0 | 0%
TOTALS | 41 | 100% | 3858 | 100% | 742189388 | 100%
STAGES OF DEVELOPMENT BY PROJECT
Stage of Development | No. of Projects | % of Total | No of Units | % of Total | Total Develop. Costs | % of Total
Prospect | 9 | 21.95% | 835 | 21.64% | 140125000 | 18.88%
Feasibility | 20 | 48.78% | 1762 | 45.67% | 332812215 | 44.84%
Development | 4 | 9.756% | 361 | 9.357% | 85100000 | 11.47%
Construction | 2 | 4.878% | 280 | 7.258% | 51536151 | 6.944%
Operations - Lease Up | 1 | 2.439% | 231 | 5.988% | 53000000 | 7.141%
Operations - Close Out | 5 | 12.2% | 389 | 10.08% | 79616022 | 10.73%
TOTALS | 41 | 100% | 3858 | 100% | 742189388 | 100%
SCHEDULE OF PROJECT CLOSINGS AND DEVELOPER FEES BY YEAR*
Year of Closing | Closings by Year | % of Total | No of Units | % of Total | Total Develop. Costs | Net Developer Fee**
2011 | 2 | 6.25% | 280 | 8.906% | 51536151 | 1404313
2012 | 4 | 12.5% | 820 | 26.08% | 161652605 | 2887333.8
2013 | 10 | 31.25% | 1120 | 35.62% | 222700060 | 4552852.5
2014 | 8 | 25% | 605 | 19.24% | 84100000 | 5563908.875
2015 | 5 | 15.62% | 170 | 5.407% | 35809550 | 6955262.875
2016 | 3 | 9.375% | 149 | 4.739% | 34975000 | 6014058.75
2017 | 0 | 0% | 0 | 0% | 0 | 3382147
2018 | 0 | 0% | 0 | 0% | 0 | 1916013.5
TOTAL | 32 | 100% | 3144 | 100% | 590773366 | 32675890.3
*Does not include projects closed before 2011 or projects with TBD closing dates
**The net developer fee is for projects closing in that year and projects closed in previous years

## 2012DevFee Budget-DO NOT CHANGE (hidden)
Project Name | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Gross Dev Fee | Contingency | Net Dev Fee
26th-Kostner/Keating | Mar: 0; Oct: 500000 | 500000 | 50% | 250000
Countryside Senior Apartments | Apr: 540000 | 540000 | 0% | 540000
Englewood Permanent Supportive Housing | [12 empty] | 0 | 0% | 0
Grayslake ILF | Sep: 310000 | 310000 | 0% | 310000
Milwaukee - Johnston Center | Jun: 310000 | 310000 | 0% | 310000
Pullman Wheelworks | [12 empty] | 0 | 0% | 0
Roseland Place | Apr: 125000; May: 42000 | 167000 | 0% | 167000
Sterling Park Apartments | Jul: 750000 | 750000 | 50% | 375000
5th Ward Senior Project/Milwaukee | [12 empty] | 0 | 0% | 0
Milwaukee Greenwich Apartments | [12 empty] | 0 | 0% | 0
YMCA Austin Avenue | [12 empty] | 0 | 0% | 0
Harold Washington Apts (LF) | [12 empty] | 0 | 0% | 0
850 N Eastwood | Jul: 750000 | 750000 | 0% | 750000
15 Year Refi of Uptown Portfolio (Miriam/Carlton) | Dec: 333333.3333 | 333333.3333 | 50% | 166666.6667
Fox River Valley | [12 empty] | 0 |  | 0
Kankakee | Dec: 420000 | 420000 | 50% | 210000
TOTAL | 0 | 0 | 0 | 665000 | 42000 | 310000 | 1500000 | 0 | 310000 | 500000 | 0 | 753333.3333 | 4080333.3333 |  | 3078666.6667

## Forecast Tracker (hidden)
| BUDGET |  |  |  | JANUARY FCAST |  |  |  | FEBRUARY FCAST |  |  |  | MARCH FCAST |  |  |  | APRIL FCAST
Project Name | Gross | Contgncy | Net | Month | Gross | Contgncy | Net | Month | Gross | Contgncy | Net | Month | Gross | Contgncy | Net | Month | Gross | Contgncy | Net | Month
26th-Kostner/Keating | 500000 | 50% | 250000 | Oct | 970682 | 50% | 485341 | Oct | 970682 | 50% | 485341 | Dec | 970682 | 50% | 485341 | Dec | 970682 | 50% | 485341 | Dec
Countryside Senior Apartments | 540000 | 0% | 540000 | Apr | 540000 | 0% | 540000 | Apr | 540000 | 0% | 540000 | Apr | 540000 | 0% | 540000 | Apr | 540000 | 25% | 405000 | May
Englewood Permanent Supportive Housing | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0
Grayslake ILF | 310000 | 0% | 310000 | Sep | 310000 | 0% | 310000 | Sep | 599488 | 90% | 59948.8 | Sep | 599488 | 90% | 59948.8 | Sep | 599488 | 90% | 59948.8 | Sep
Milwaukee - Johnston Center | 310000 | 0% | 310000 | Jun | 307201 | 0% | 307201 | Jun | 307201 | 0% | 307201 | Jun | 307201 | 0% | 307201 | Jun | 307201 | 0% | 307201 | Jun
Pullman Wheelworks | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0
Roseland Place | 167000 | 0% | 167000 | Apr, May | 287786 | 0% | 287786 | Feb, May | 287786 | 0% | 287786 | Feb, May | 287786 | 0% | 287786 | Feb, May | 287786 | 0% | 287786 | May
Sterling Park Apartments | 750000 | 50% | 375000 | Jul | 750000 | 50% | 375000 | Nov | 750000 | 50% | 375000 | Nov | 750000 | 50% | 375000 | Nov | 750000 | 50% | 375000 | Nov
5th Ward Senior Project/Milwaukee | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0
Milwaukee Greenwich Apartments | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0
YMCA Austin Avenue | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0
Harold Washington Apts (LF) | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0 |  | 0 | 0% | 0
850 N Eastwood | 750000 | 0% | 750000 | Jul | 750000 | 15% | 637500 | Jul | 750000 | 15% | 637500 | Jul | 750000 | 15% | 637500 | Jul | 750000 | 15% | 637500 | Jul
15 Year Refi of Uptown Portfolio (Miriam/Carlton) | 333333.3333 | 50% | 166666.6667 | Dec | 333333.3333 | 50% | 166666.6667 | Dec | 333333.3333 | 50% | 166666.6667 | Dec | 333333.3333 | 50% | 166666.6667 | Dec | 333333.3333 | 50% | 166666.6667 | Dec
Fox River Valley | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Kankakee | 420000 | 50% | 210000 | Dec | 420000 | 50% | 210000 | Dec | 226256 | 50% | 113128 | Dec | 0 | 50% | 0 | Oct 2013 | 0 | 50% | 0 | Oct 2013
Danville VA |  |  |  |  | 400000 | 50% | 200000 | Dec | 325781 | 50% | 162890.5 | Dec | 325781 | 50% | 162890.5 | Dec | 325781 | 50% | 162890.5 | Dec
TOTAL | 4080333.3333 |  | 3078666.6667 |  | 5069002.3333 |  | 3519494.6667 |  | 5090527.3333 |  | 3135461.9667 |  | 4864271.3333 |  | 3022333.9667 |  | 4864271.3333 |  | 2887333.9667
Variance |  |  |  |  | 988669 |  | 440828 |  | 1010194 |  | 56795.3 |  | 783938 |  | -56332.7 |  | 783938 |  | -191332.7

## Detail
|  |  | Drop Down | Drop Down | Drop Down | Hidden |  | Drop Down | Drop Down | Drop Down | Drop Down | [9 empty] | Drop Down | Drop Down | Drop Down | Drop Down | Drop Down | Drop Down | If Formula, Orange Text | If Formula, Orange Text | If Formula, Orange Text |  | If Formula, Orange Text |  | If Formula, Orange Text | If Formula, Orange Text | If Formula, Orange Text
|  |  | Acquisition/ Rehab | Multi-Family | Construction |  |  | Conventional Financing | AHP | AHP | AHP |  |  | 2011 | [6 empty] | Family | Diabled | Disabled - Chronically Mentally Ill | Family | Case Management - In House | Government Contracts
|  |  | Adaptive/ Rehab | Single-Family | Development |  |  | Public Grant | Bond | Bond | Bond |  |  | 2012 | [6 empty] | Senior | Homeless | Disabled - Developmentally | Supportive | Case Management - 3rd party | Property Operations
|  |  | New Construction |  | Feasibility |  |  | HUD 202 | CDBG | CDBG | CDBG |  |  | 2013 | [6 empty] | Special Needs (PSH) | Senior - Frail | Disabled - Physically | Seniors | Service Coordination | Philanthropy
|  |  | Refinance/ Rehab |  | Operations - Sub Phase Lease Up |  |  | HUD 811 | Federal: HUD | Federal: HUD | Federal: HUD |  |  | 2014 | [6 empty] | For Sale | Senior - Independent | Dual Diagnosis | N/A | Program - In House | 3rd Party
|  |  | Rehab |  | Operations - Sub Phase Close Out |  |  | LIHTC - 4% | USDA | USDA | USDA |  |  | 2015 | [7 empty] | Vets | Homeless | TBD | Program - 3rd Party | TBD
[5 empty] | Prospect |  |  | LIHTC - 9% | Federal: VA | Federal: VA | Federal: VA |  |  | 2016 | [7 empty] | Workforce | Vets |  | TBD | N/A
[5 empty] | Listed For Sale |  |  | USDA | HOME | HOME | HOME | [10 empty] | Special Needs | Special Needs |  | N/A
[5 empty] | Under Contract |  |  | Opportunity Zone | LIHTC - 4% | LIHTC - 4% | LIHTC - 4% | [10 empty] | TBD | TBD
[8 empty] | Foundation Grant | LIHTC - 9% | LIHTC - 9% | LIHTC - 9% | [10 empty] | N/A | N/A
[9 empty] | City/ County Funding | City/ County Funding | City/ County Funding
[9 empty] | Local: Other | Local: Other | Local: Other
[9 empty] | State Funding | State Funding | State Funding
[9 empty] | NSP | NSP | NSP
[9 empty] | TCAP | TCAP | TCAP
[9 empty] | Opportunity Zone | Opportunity Zone | Opportunity Zone
[9 empty] | Foundation Grant | Foundation Grant | Foundation Grant
[9 empty] | Other Partners | Other Partners | Other Partners
DEVELOPMENT PIPELINE DETAIL
DEVELOPER FEES
Project | Developer | City | Construction Type | Asset Class | Development Stage | No. ( for fomula in Pipeline Summary) | Acquisition Costs | Financing - Primary | Financing - 2nd | Financing - 3rd | Financing - 4th | App Yr | Date Tax Credits Awarded | Close Year | Date of Close | % Complete | Est Start Construction | Est End Construction | Number of Units | Form of Site Control | Population Served - Primary | Population Served - 2nd | Population Served - 3rd | Resident Services Program Model | Resident Services Type | Primary Source of Service Funding | EST TDC for Phase (in millions) | TOTAL Estimated Tax Credit Award | ANNUAL Estimated Tax Credit Award | $/Credit | TOTAL Estimated Tax Credit Equity | Tax Credit Investor | Est Gross Developer Fee | Est DDF | Est Paid Developer Fee | Other Fees | EST % Afford | Management Company | JV/Sole | 2008 | 2009 | 2010 | 2011 | Actual Jan 2012 | Actual Feb 2012 | Actual 3/1/2012 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2012 | Cntgncy | Net 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
26th & Kostner/Keating | L Brace | Chicago | Adaptive/ Rehab | Multi-Family | Prospect | 1 | 8980000 | LIHTC - 4% | Local: City/County Funding | Local: City/County Funding | Local: City/County Funding | 2011 | Self Generated at Closing | 2012 | 2012-12-01 | 0% | 2012-12-01 | 2014-09-01 | 125 | PSA | Family | Workforce | Vets | Family | Service Coordination | TBD | 52200000 | 17540000 | 1754000 | 0.9 | 15786000 | TBD | 5176969 | 1294242.25 | 3882726.75 |  | 100% | MHMG | Boulevard Group | [13 empty] | 970682 |  |  | 970682 | 50% | 485341 |  | 1941363.375 | 970681.375
Countryside Senior Apts | L Reyes | Countryside | New Construction | Single-Family | Operations - Sub Phase Close Out | 1 | 1600000 | LIHTC - 9% | Local: City/County Funding | Grant Funding - Public or Private | N/A | 2008 | 2009 | 2009 | 2009-09-01 | 100% | 2009-09-01 | 2010-09-01 | 70 | Ground Lease | Senior | Senior - Independent | N/A | Seniors | Service Coordination | Property Operations | 16101522 | 10908330 | 1090833 | 0.74 | 8104760 | B of A | 1129550 | 0 | 1129550 |  | 90% | MHMG | IFF |  | 204386 | 190760.5 | 192403 |  |  |  | 540000 | [8 empty] | 540000 | 25% | 405000
Grayslake Senior | L Reyes | Grayslake | New Construction | Multi-Family | Construction | 1 | 730000 | LIHTC - 9% | AHP | Grant Funding - Public or Private | Grant Funding - Public or Private | 2011 | 2009 | 2011 | 2011-11-02 | 40% | 2011-11-01 | 2012-11-01 | 70 | Own | Senior | Senior - Independent | Disabled - Chronically Mentally Ill | Seniors | Service Coordination | TBD | 21400000 | 20607000 | 2060700 | 0.93 | 19164510 | Enterprise/ JP Morgan | 2030316 | 507579 | 1522737 |  | 100% | MHMG | Sole |  |  |  | 445719 | [8 empty] | 599488 |  |  |  | 599488 | 90% | 59948.8 | 477530
Milwaukee - Johnston Center | D Lyon | Milwaukee | Adaptive/ Rehab | Multi-Family | Operations - Sub Phase Close Out | 1 | 798500 | LIHTC - 9% | TCAP | AHP | Local: City/County Funding | 2008/09 | 2009 | 2009 | 2009-12-01 | 100% | 2009-11-01 | 2010-10-01 | 91 | Offer | Special Needs (PSH) | Homeless | Dual Diagnosis | Supportive | Case Management - 3rd party | Government Contracts | 13848000 | 13750000 | 1375000 | 0.69 | 9486600 | US Bank | 1436566.7356 | 0 | 1436566.7356 |  | 100% | MHMG | Sole |  | 361274 | 334556.9823 | 434799 | [5 empty] | 307201 | [6 empty] | 307201 | 0% | 307201
Pullman Wheelworks | L Brace | Chicago | Acquisition/ Rehab | Multi-Family | Construction | 1 | 14000000 | LIHTC - 4% | Local: State Funding | Local: City/County Funding | Grant Funding - Public or Private | 2010 | 2011 | 2011 | 2011-12-01 | 5% | 2011-12-31 | 2013-09-01 | 210 | PSA | Family | Workforce | N/A | Family | Service Coordination | Property Operations | 30136151 | 8618590 | 861859 | 0.88 | 8320580 | National Affordable Housing Trust | 2976286 | 1876286 | 1100000 |  | 100% | Leasing and Mgmt Corp. | NHT-E |  |  |  | 275000 | [12 empty] | 0 |  | 0 | 440000 | 385000
Roseland Place | L Reyes | Chicago | New Construction | Multi-Family | Operations - Sub Phase Close Out | 1 | 680000 | HUD 202 | LIHTC - 9% | Local: State Funding | Grant Funding - Public or Private | 2009 | 2009 | 2009 | 2009-12-01 | 100% | 2009-12-01 | 2011-03-01 | 60 | JV | Senior | Senior - Independent | N/A | Seniors | Service Coordination | Government Contracts | 17786000 | 8442046 | 844204.6 | 0.8 | 6753638 | B of A | 700570 | 0 | 700570 |  | 100% | MHMG | NHS |  | 356391.5 |  | 56392 |  |  |  |  | 287786 | [7 empty] | 287786 | 0% | 287786
Sterling Park | M Angelini | Chicago | Adaptive/ Rehab | Multi-Family | Development | 1 | 5800000 | LIHTC - 4% | Local: City/County Funding | Grant Funding - Public or Private | N/A | 2012 | Self Generated at Closing | 2012 | 2012-11-01 | 0% | 2012-12-01 | 2014-12-01 | 181 | JV | Family | Workforce | N/A | Family | Service Coordination | TBD | 45700000 | 14400310 | 1440031 | 0.95 | 13680294.5 | TBD | 2718225 | 1718225 | 1000000 |  | 100% | MHMG | Royal Imperial | [14 empty] | 750000 |  | 750000 | 50% | 375000 |  | 200000 | 500000
5th Ward Senior Project/ Milwaukee | D Lyon | Milwaukee | New Construction | Multi-Family | Development | 1 | 780000 | LIHTC - 9% | Local: Other | TBD | N/A | 2013 | TBD | 2013 | 2013-12-01 | 0% | 2014-01-01 | 2015-01-01 | 55 | PSA | Senior | Senior - Independent | N/A | Seniors | Service Coordination | TBD | 9500000 | 10500000 | 1050000 | 0.9 | 9450000 | TBD | 889000 | 222250 | 666750 |  | 100% | MHMG | Sole | [16 empty] | 0 |  |  | 166687.5 |  | 166687.5 | 266700 | 66675
Milwaukee Greenwich Apartments | D Lyon | Milwaukee | New Construction | Multi-Family | Development | 1 | 120000 | LIHTC - 9% | TBD | TBD | TBD | 2013 | TBD | 2013 | 2013-12-01 | 0% | 2014-01-01 | 2015-01-01 | 55 | PSA | Family | Workforce | N/A | Family | Service Coordination | TBD | 11000000 | 10500000 | 1050000 | 0.9 | 9450000 | TBD | 1052000 | 263000 | 789000 |  | 100% | MHMG | Sole | [16 empty] | 0 |  |  | 197250 |  | 197250 | 315600 | 78900
YMCA Austin | L Brace | Chicago | New Construction | Multi-Family | Prospect | 1 | Donated | LIHTC - 9% | TBD | TBD | TBD | TBD | TBD | 2013 | 2013-10-01 | 0% | 2013-10-01 | 2015-04-01 | 160 | MOU | Special Needs (PSH) | Homeless | Dual Diagnosis | Supportive | Case Management - In House | TBD | 32000000 | 24000000 | 2400000 | 0.78 | 18720000 | TBD | 3104000 | 2104000 | 1000000 |  | 100% | MHMG | Heartland | [16 empty] | 0 |  | 0 | 150000 | 300000 |  | 400000
Harold Washington Apts | M Angelini | Chicago | Refinance/ Rehab | Multi-Family | Operations - Sub Phase Close Out | 1 | 3100000 | LIHTC - 4% | Local: City/County Funding | Local: State Funding | N/A | 2009 | 2009 | 2010 | 2010-08-01 | 95% | 2010-09-01 | 2012-03-01 | 69 | Own | Special Needs (PSH) | Homeless | Dual Diagnosis | Supportive | Case Management - In House | Government Contracts | 15100000 | 4638364.6053 | 463836.4605 | 0.76 | 3525157.1 | B of A | 1757000 | 760000 | 997000 |  | 100% | MHMG | Sole | [16 empty] | 0
850 N Eastwood | M Angelini | Chicago | Acquisition/ Rehab | Multi-Family | Operations - Sub Phase Lease Up | 1 | 20500000 | LIHTC - 4% | Local: City/County Funding | Local: State Funding | N/A | 2009 | 2009 | 2010 | 2010-08-01 | 95% | 2010-08-01 | 2012-03-01 | 231 | PSA | Family | Workforce | N/A | Family | Service Coordination | Property Operations | 53000000 | 15528440 | 1552844 | 0.76 | 11801612.9 | B of A | 5882000 | 5879000 | 3000 |  | 88.31% | Leasing & Mgmt Corp. | Sole |  |  | 172500 | [7 empty] | 750000 | [5 empty] | 750000 | 15% | 637500 | 171000 | 183000 | 195000 | 207000
15 Year Refi-Uptown Portfolio | M Angelini & A Blakley | Chicago | Refinance/ Rehab | Multi-Family | Feasibility | 1 | 0 | LIHTC - 4% | Bond | Local: City/County Funding | Local: State Funding | 2012 | Self Generated at Closing | 2012 | 2012-12-01 | 0% | 2013-01-01 | 2014-04-01 | 449 | Own | Special Needs (PSH) | Homeless | Dual Diagnosis | Supportive | Case Management - In House | TBD | 43752605 | 13663550 | 1366355 | 0.9 | 12297195 | TBD | 3047000 | 1523500 | 1523500 | 732106 | 100% | MHMG | Sole | [15 empty] | 333333 | 333333 | 50% | 166666.5 |  | 600000 | 590167
Kankakee | L Reyes | Kankakee | New Construction | Multi-Family | Development | 1 | 1335500 | LIHTC - 9% | TBD | TBD | TBD | 2012 | TBD | 2013 | 2013-10-01 | 0% | 2013-10-01 | 2014-10-01 | 70 | PSA | Senior | Senior - Independent |  | Seniors | Service Coordination | TBD | 18900000 | 18000156 | 1800015.6 | 0.9199 | 16558343.5044 | Enterprise/ Fifth Third | 1743353 | 486373 | 1256980 |  | 100% | MHMG | TBD | [15 empty] | 0 | 0 |  | 0 | 226256
Johnston Center 2 | D Lyon | Milwaukee | New Construction | Multi-Family | Prospect | 1 | 650000 | LIHTC - 9% | TBD | TBD | TBD | 2013 | TBD | 2013 | 2013-12-01 | 0% | 2014-01-01 | 2015-01-01 | 55 | none | Family | Homeless | Vets | Supportive | Case Management - 3rd party | TBD | 9625000 | TBD | TBD |  | TBD | TBD | 900000 | 225000 | 675000 |  | 100% | MHMG | Sole | [16 empty] | 0 |  |  | 168750 |  | 168750 | 270000 | 67500
Danville VA Hospital Site | D Lyon | Danville | New Construction | Multi-Family | Feasibility | 1 | 0 | LIHTC - 9% | Local: State Funding | Grant Funding - Public or Private | Grant Funding - Public or Private | 2012 | TBD | 2012 | 2012-12-01 | 0% | 2013-01-01 | 2013-12-31 | 65 | Land Lease | Special Needs (PSH) | Vets | Homeless | Supportive | Case Management - 3rd party | TBD | 20000000 | 18500000 | 1850000 | 0.934 | 17279000 | TBD | 1737500 | 434375 | 1303125 |  | 100% | MHMG | Sole | [15 empty] | 325781 | 325781 | 50% | 162890.5 |  | 325781.25 | 521250 | 130312.5
Children's Memorial Site | M Angelini | Chicago | Adaptive/ Rehab | Multi-Family | Prospect | 1 | 2000000 | LIHTC - 9% | TBD | TBD | TBD | 2013 | TBD | 2013 | 2013-03-01 | 0% | 2013-03-01 | 2014-06-01 | 95 | none | Senior | Senior - Independent | N/A | Seniors | Service Coordination | TBD | 17500000 | 13125000 | 1312500 | 0.72 | 9450000 | TBD | 1750000 | 437500 | 1312500 |  | 100% | MHMG | Sole | [16 empty] | 0 |  | 0 | 750000 |  | 250000
Englewood Apartments | M Angelini | Chicago | New Construction | Multi-Family | Operations - Sub Phase Close Out | 1 | 0 | LIHTC - 9% | Local: City/County Funding | HOME | N/A | 2008 | 2008 | 2008 | 2008-12-01 | 100% | 2008-12-01 | 2010-09-01 | 99 | Own | Special Needs (PSH) | Homeless | Dual Diagnosis | Supportive | Case Management - In House | Government Contracts | 16780500 | 12585375 | 1258537.5 | 0.91 | 11452691.25 | US Bank | 1000000 | 640000 | 360000 |  | 100% | MHMG | Sole | 360000 | [15 empty] | 0
Menomonee River Valley | D Lyon | Milwaukee | New Construction | Multi-Family | Prospect | 1 | TBD | LIHTC - 9% | TBD | TBD | TBD | TBD | TBD | 2014 | 2014-12-01 | 0% | 2014-12-01 | 2016-02-01 | 60 | TBD | Family | Workforce | N/A | Family | Service Coordination | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD |  | TBD | MHMG | TBD | [16 empty] | 0 |  |  |  | 250000 |  | 450000
Pullman Wheelworks, Phase 2 | M Angelini | Chicago | New Construction | Multi-Family | Prospect | 1 | TBD | LIHTC - 9% | TBD | TBD | TBD | TBD | TBD | 2014 | 2014-12-01 | 0% | 2014-12-01 | 2016-03-01 | 60 |  | Senior | Senior - Independent | Vets | Seniors | Service Coordination | TBD | TBD | TBD | TBD |  | TBD | TBD | TBD | TBD | TBD |  | TBD | MHMG | TBD | [16 empty] | 0 |  |  |  | 250000 |  | 450000
Danville VA Hospital Site - Phase 2 | D Lyon | Danville | New Construction | Multi-Family | Feasibility | 1 | Land Lease | LIHTC - 9% | Local: State Funding | Grant Funding - Public or Private | TBD | 2014 | TBD | 2014 | 2014-12-01 | 0% | 2015-01-01 | 2015-12-01 | 65 | Land lease | Special Needs (PSH) | Homeless | Vets | Supportive | Service Coordination | TBD | 20000000 | 18500000 | 1850000 | 0.934 | 17279000 | TBD | 1737500 | 434375 | 1303125 |  | 100% | MHMG | Sole | [16 empty] | 0 |  |  |  | 325781.25 |  | 325781.25 | 521250 | 130312.5
Westside Resyndication | A Blakley | Chicago | Refinance/ Rehab | Multi-Family | Feasibility | 1 | 0 | LIHTC - 4% | TBD | TBD | TBD | 2013 | TBD | 2013 | 2013-12-01 | 0% | 2013-12-01 | 2015-03-01 | 315 | Own | Family | Workforce | N/A | Family | Program - In House | Property Operations | 30712500 | 9213750 | 921375 | 0.72 | 6633900 | TBD | 2979112.5 | 1979113 | 999999.5 |  | 100% | MHMG | Sole | [16 empty] | 0 |  | 0 | 250000 | 350000 | 400000
MuskegonTrinity site |  | Muskegon, MI | Adaptive/ Rehab | Multi-Family | Feasibility | 1 | TBD | [6 empty] | 2015 | [6 empty] | Family |  |  | Family |  | TBD | [11 empty] | MHMG | [17 empty] | 0 |  |  |  |  | 500000 |  | 500000
Mercy Housing/Ickes Site |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | TBD | [6 empty] | 2015 | [6 empty] | Family |  |  | Family |  | TBD | [11 empty] | MHMG | [17 empty] | 0 |  |  |  |  | 500000 |  | 500000
Sisters of St Casimir facility |  | Chicago | Acquisition/ Rehab | Multi-Family | Feasibility |  | TBD | [13 empty] | Senior |  |  | Seniors | [31 empty] | 0
0
0
0
0
0
PIPELINE TOTALS | [39 empty] | 360000 | 922051.5 | 697817.4823 | 1404313 | 0 | 0 | 0 | 540000 | 287786 | 307201 | 750000 | 0 | 599488 | 970682 | 750000 | 659114 | 4864271 |  | 2887333.8 | 2997473.5 | 5110925.875 | 4959785.875 | 2815393.75 | 1734325 | 130312.5
PROJECTS NOT IN ACTIVE PIPELINE
MHL-NNCHC ILF |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | 0 | LIHTC - 4% |  |  |  | 2013 |  | 2014 | 2014 | 0% |  | 2014 | 80 | JV | Senior | [5 empty] | 20000000 | 6000000 |  | 0.72 | 4320000 |  | 1940000 | 940000 | 1000000 |  | 100% |  | NNCHC | [18 empty] | 0
Homan Square (Phase 2) |  | Chicago | Acquisition/ Rehab | Multi-Family | Feasibility | 1 | 8000000 | LIHTC - 4% |  |  |  | 2012 |  | 2013 | 2013 | 0% |  | 2015 | 195 | JV | Family | [5 empty] | 53625000 | 16087500 |  | 0.72 | 11583000 |  | 5201625 | 2000000 | 3201625 |  | 80% |  | Royal Imperial | [18 empty] | 0 | 709500 |  | 473000 | 1182500
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | LIHTC - 9% |  |  |  | 2013 |  | 2013 | 2013 | 0% |  | 2015 | 60 | MOA | Senior | [5 empty] | 15300000 | 11475000 |  | 0.72 | 8262000 |  | 1484100 | 484100 | 1000000 |  | 80% |  | Sole | [18 empty] | 0 | 300000 |  | 200000 | 500000
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | LIHTC - 4% |  |  |  | 2014 |  | 2014 | 2014 | 0% |  | 2016 | 60 | MOA | Senior | [5 empty] | 15300000 | 4590000 |  | 0.72 | 3304800 |  | 1484100 | 484100 | 1000000 |  | 80% |  | Sole | [18 empty] | 0 |  | 300000 |  | 200000 | 500000
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | HUD 202 |  |  |  | 2015 |  | 2015 | 2015 | 0% |  | 2017 | 60 | MOA | Family | [5 empty] | 15300000 | 0 |  | 0.72 | 0 |  | 1484100 | 484100 | 1000000 |  | 80% |  | Sole | [18 empty] | 0 |  |  | 300000 |  | 200000 | 500000
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | LIHTC - 9% |  |  |  | 2016 |  | 2016 | 2016 | 0% |  | 2018 | 60 | MOA | Special Needs (PSH) | [5 empty] | 15300000 | 11475000 |  | 0.72 | 8262000 |  | 1484100 | 484100 | 1000000 |  | 80% |  | Sole | [18 empty] | 0 |  |  |  | 300000 |  | 200000
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | Conventional Financing |  |  |  | 2016 |  | 2016 | 2016 | 0% |  | 2018 | 14 | MOA | For Sale | [5 empty] | 2800000 | 0 |  | 0.72 | 0 |  | 271600 | 67900 | 203700 |  | 80% |  | Sole | [18 empty] | 0 |  |  |  |  | 300000
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | Conventional Financing |  |  |  | 2017 |  | 2017 | 2017 | 0% |  | 2019 | 38 | MOA | For Sale | [5 empty] | 7600000 | 0 |  | 0.72 | 0 |  | 737200 | 184300 | 552900 |  | 80% |  | Sole | [18 empty] | 0 | [5 empty] | 300000
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | Conventional Financing |  |  |  | 2017 |  | 2017 | 2017 | 0% |  | 2020 | 28 | MOA | For Sale | [5 empty] | 5600000 | 0 |  | 0.72 | 0 |  | 543200 | 135800 | 407400 |  | 80% |  | Sole | [18 empty] | 0
26th & Kostner |  | Chicago | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | Conventional Financing |  |  |  | 2018 |  | 2018 | 2018 | 0% |  | 2021 | 28 | MOA | For Sale | [5 empty] | 5600000 | 0 |  | 0.72 | 0 |  | 543200 | 135800 | 407400 |  | 80% |  | Sole | [18 empty] | 0
Copley Site (Phase 1) |  | Aurora | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | LIHTC - 9% |  |  |  | 2012 |  | 2013 | 2013 | 0% |  | 2015 | 60 | MOU | Senior | [5 empty] | 24537560 | 18403170 |  | 0.72 | 13250282.4 |  | 2426130.9729 | 606532.7432 | 1819598.2297 |  | 90% |  | Sole | [18 empty] | 0 | 545879 |  | 727839 | 545879
Copley Site |  | Aurora | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | Conventional Financing |  |  |  | 2014 |  | 2015 | 2015 | 0% |  | 2016 | 60 | non | Senior | [5 empty] | 13500000 | 0 |  | 0.72 | 0 |  | 1309500 | 327375 | 982125 |  | 90% |  | Sole | [18 empty] | 0 |  |  | 294638 |  | 392850 | 294638
Copley Site |  | Aurora | New Construction | Multi-Family | Feasibility | 1 | JV - Contrib | LIHTC - 4% |  |  |  | 2016 |  | 2016 | 2016 | 0% |  | 2017 | 75 | none | Senior | [5 empty] | 16875000 | 5062500 |  | 0.72 | 3645000 |  | 1636875 | 409218.75 | 1227656.25 |  | 90% |  | Sole | [18 empty] | 0 |  |  |  | 368297 |  | 491063
Indianapolis SRO PSH | D Lyon | Indianapolis | New Construction | Multi-Family | Prospect | 1 |  | LIHTC - 9% |  |  |  | 2013 |  | 2014 | 2014 | 0% |  |  | 60 |  | Family | Homeless | Vets | Supportive | [5 empty] | 0.72 | 0
Danville Indep Senior | D Lyon | Danville | New Construction | Multi-Family | Feasibility | 1 | Donated | HUD 202 |  |  |  | 2014 |  | 2015 | 2015 | 0% |  | 2016 | 50 | none | Senior | [5 empty] | 7009550 | 0 |  | 0.72 | 0 |  | 679926.35 | 169981.5875 | 509944.7625 |  | 100% |  | Sole | [18 empty] | 0 |  | 152983 |  | 101989 | 254972
Jefferson Barracks | D Lyon | St Louis | Acquisition/ Rehab | Multi-Family | Prospect | 1 | TBD | LIHTC - 9% | Federal: VA |  |  | TBD |  | 2014 | 2014 | 0% |  | TBD | 60 | TBD | Family | Homeless | Vets | Supportive |  |  | TBD | TBD |  | 0.72 | TBD |  | TBD | TBD | TBD |  | TBD |  | TBD | [18 empty] | 0
Kane County Health Dept/COA | L Reyes | Aurora | New Construction | Multi-Family | Prospect | 1 | 1600000 | LIHTC - 9% |  |  |  | TBD |  | 2014 | 2014 | 0% |  | TBD | 160 | none | Special Needs (PSH) | Homeless | Dual Diagnosis | Supportive |  |  | 28800000 | 0 |  | 0.72 | 0 |  | 2793600 | 698400 | 2095200 |  | 100% |  | Sole | [18 empty] | 0
[41 empty] | 0 | 0 | 0 | [12 empty] | 0 |  | 0 | 1555379 | 452983 | 1995477 | 3198665 | 1647822 | 1785701
[41 empty] | 922051.5 | 697817.4823 | 1404313 | [12 empty] | 4864271 |  | 2887333.8 | 4552852.5 | 5563908.875 | 6955262.875 | 6014058.75 | 3382147 | 1916013.5
PROJECTS TRANSFERRED TO ASSET MANAGEMENT AND OUT OF ACTIVE PIPELINE
Galewood SLF | A Blakley | Chicago | New Construction |  |  | 1 | 0 | LIHTC - 9% | Local: City/County Funding | HOME | AHP | 2007 |  | 2007 | 2007-11-01 | 100% | 2007-11-01 | 2009-02-01 | 102 | JV | Senior | Senior - Frail |  | N/A |  |  | 23970000 | 17977500 |  | 0.81 | 14561775 |  | 482119 | 322972 | 159147 |  | 50% | Pathways | JV | 59204 | 3123 |  | 187126
Malden Arms | B Thapar | Chicago | Refinance/Rehab |  |  | 1 | 0 | 09-C | LIHTC - 9% |  |  | 2007 |  | 2008 | 2008 |  |  | 2009 | 83 | Own | Special Needs (PSH) | Homeless | Dual Diagnosis | Supportive | Case Management - In House |  | 6500000 | 0 |  | 0.84 | 0 |  | 520000 | 0 | 520000 |  | 100% | MHMG | Sole | 208000 | 256000
DEAD DEALS
Prince Hall (Phase 1) |  | Milwaukee | New Construction |  | Prospect | 1 | 435600 | LIHTC - 9% |  |  |  | 2012 |  | 2013 | 2013 | 0% |  | 2013 | 55 | TBD | Senior | [5 empty] | 9625000 | 7218750 |  | 0.72 | 5197500 |  | 962500 | 240625 | 721875 |  | 100% |  | Sole | [18 empty] | 0
Prince Hall |  | Milwaukee | New Construction |  | Prospect | 1 | 0 | LIHTC - 9% |  |  |  | 2012 |  | 2013 | 2013 | 0% |  | 2013 | 55 | TBD | Senior | [5 empty] | 9625000 | 7218750 |  | 0.72 | 5197500 |  | 962500 | 240625 | 721875 |  | 100% |  | Sole | [18 empty] | 0
Prince Hall |  | Milwaukee | New Construction |  | Prospect | 1 | 0 | LIHTC - 9% |  |  |  | 2014 |  | 2014 | 2014 | 0% |  | 2015 | 55 | TBD | Family | [5 empty] | 9625000 | 7218750 |  | 0.72 | 5197500 |  | 962500 | 240625 | 721875 |  | 100% |  | Sole | [18 empty] | 0
Library Mall |  | Milwaukee | New Construction |  | Prospect | 1 | 0 | LIHTC - 9% |  |  |  | 2013 |  | 2014 | 2014 | 0% |  | 2014 | 55 | TBD | Senior | [5 empty] | 9625000 | 7218750 |  | 0.72 | 5197500 |  | 962500 | 240625 | 721875 |  | 100% |  | Sole | [18 empty] | 0 | 366660 |  | 244440 | 611100
Milwaukee Enterprise Center WFR | D Lyon | Milwaukee | Adaptive/ Rehab |  | Prospect | 1 | TBD | LIHTC - 9% | TBD | TBD | TBD | 2013 |  | 2013 | 2013-12-01 | 0% | 2014-01-01 | 2015-01-01 | 55 | none | Family | Homeless | Vets | Supportive | Case Management - 3rd party | TBD | 9625000 | TBD | TBD |  | TBD |  | 900000 | 225000 | 675000 |  | 100% | MHMG | Sole | [19 empty] | 168750 |  | 168750 | 270000 | 67500
TOTALS | [5 empty] | 3 | [12 empty] | 219 | [7 empty] | 16780500 | 12585375 |  |  | 11452691.25 |  | 1000000 | 640000 | 360000
Note on AF26: lbrace: LIHTC equity only.
Note on BE26: May change to $970,682 (25% of TDC) and change to Dec 12
Note on BF27: tmastracci: Changed to 25% per the negative adjuster amd beiong conservative per Jane
Note on BF28: tmastracci: changed to 50% per 1st quarter financial memo - Jane asked to move back to 90%
Note on AK38: Construction Guarantee Fee
Note on BD39: tmastracci: $225,256 was moved to October 2013
Note on A71: mangelini: the three phases of copley should go away … we can do that after the current budget projections exercise more thoughtfully as to what we’d replace them with

## Operational P&L
|  | YEAR 2015 |  |  |  |  | YEAR 2016 |  |  |  |  | SAMPLE OPERATING BUDGET
|  | Development | Asset Mgmt | Property Mgmt | Vice President | Total | Development | Asset Mgmt | Property Mgmt | Vice President | Total | Development | Asset Mgmt | Property Mgmt | Vice President | Total
Revenue
Property Mgmt Fees | [5 empty] | 735599.36 |  |  |  |  | 809578.22 |  |  |  |  | 0
Bookkeeping Fees | [5 empty] | 43271.62 |  |  |  |  | 62104.8 |  |  |  |  | 0
Accrued Developer Fees | [5 empty] | 1842423.4 |  |  |  |  | 1426757.45
Cash Pipeline Developer Fees | [5 empty] | 4959785.875 |  |  |  |  | 2815393.75 |  |  |  |  | 1734325
Seller Note Revenue | [5 empty] | N/A |  |  |  |  | N/A |  |  |  |  | 0
Total Revenue | [5 empty] | 2621294.38 |  |  |  |  | 2298440.47 |  |  |  |  | 1734325
Direct Affordable Housing Expenses
Salaries |  | 294269.49 | 412396.99 | 324014.87 | 193119.02 | 1223800.37 | 340834.2 | 481296.42 | 388495.05 | 210177.52 | 1420803.19 | 304266.66 | 594387.15 | 495944.1 | 122021.06 | 1516618.97
Benefits |  | 60320.78 | 208658.19 | 142863.53 | 50867.99 | 462710.49 | 116005.68 | 231785.91 | 148686.41 | 46860.8524 | 543338.8524 | 75596.4277 | 182755.0392 | 142689.2042 | 13847.42 | 414888.0911
[6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Supplies | 52000 | 290.39 | 24.96 | 555.68 |  | 871.03 | 5.7 | 85.61 | 69.63 |  | 160.94 |  |  | 230.5271 |  | 230.5271
Travel-Reimb | 56000 | 32015.91 | 21671.33 | 33390.38 | 19121.09 | 106198.71 | 31655.38 | 30930.19 | 58497.79 | 18597.48 | 139680.84 | 21879.4165 | 65718.6776 | 40353.9247 | 5294.01 | 133246.0288
Staff Develop | 57000 | 3071.71 | 2518.78 | 9.91 |  | 5600.4 | 2627.33 | 1454.1 | 80 |  | 4161.43 | 533.6471 |  |  |  | 533.6471
Contract Services | 58000 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1405.8071 | 210.3529 |  | 1616.16
Choller Consulting | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 29532.165 | 29532.165
C/Serv-Shared Emp | 58800 |  |  |  |  | 0 |  | 4263.08 |  |  | 4263.08 |  |  | 487.9059 |  | 487.9059
Employee Recruitment | 64000 |  |  |  |  | 0 |  |  | 3500 |  | 3500 |  |  |  |  | 0
Dues-Reimb | 64025 | 980.33 |  |  |  | 980.33 | 10750 |  |  |  | 10750 | 12750 |  |  |  | 12750
Telecommuters | 64234 | 993.45 | 281.91 | 1523.76 |  | 2799.12 | 1685.3 |  | 2641.48 |  | 4326.78 | 401.77 | 30 | 1913.4635 |  | 2345.2335
Emp Rel-Reimb | 64300 | 311.69 | 484.53 | 53.2 |  | 849.42 | 167.62 | 808.44 |  |  | 976.06 | 154.0376 | 267.2753 | 199.7365 |  | 621.0494
Public Rel-Reimb | 64340 |  |  | 193.19 |  | 193.19 |  |  |  |  | 0 |  |  |  |  | 0
Pro Services | 64360 |  | 700 |  |  | 700 | 10680.08 | 1050 |  |  | 11730.08 | 7247.3506 |  | 1129.4118 |  | 8376.7624
Meetings | 64800 | 393.1 | 47.17 | 100.07 |  | 540.34 | 564.81 |  | 357.26 |  | 922.07 | 69.4588 | 306.7059 | 99.1765 |  | 475.3412
Workshops | 64802 | 1194.73 | 165.36 |  |  | 1360.09 | 64.46 | 1530.59 |  |  | 1595.05 |  |  |  |  | 0
HUD Facility Exp | 64876 | 252673.37 | 6000 | 9915.62 |  | 268588.99 | 65721.93 | 39787.98 | 13679.38 |  | 119189.29 | 100000 | 50735.2518 | 782.9082 |  | 151518.16
Total Direct Aff Housing Expenses |  | 646514.95 | 652949.22 | 512620.21 | 263108.1 | 2075192.48 | 580762.49 | 792992.32 | 616007 | 275635.8524 | 2265397.6624 | 522898.7683 | 895605.9068 | 684040.7113 | 170694.655 | 2273240.0413
Net Income/(Loss) Before Service Line Allocation | [5 empty] | 546101.9 |  |  |  |  | 33042.8076 |  |  |  |  | -538915.0413
Nation Campus Service Line Allocation (Budgeted Numbers) | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Net Income/(Loss) Accrual After Service Line Allocation | [5 empty] | 546101.9 |  |  |  |  | 33042.8076
Net Income/(Loss) Cash After Service Line Allocation | [5 empty] | 3663464.375 |  |  |  |  | 1421679.1076 |  |  |  |  | -538915.0413
Note on L30: Susan Beaman: Removed $100,000 for recently approved surplus cash note for Lincoln Villas. Need to confirm amount

## Reporting Summary RVSD
REAL ESTATE DEVELOPMENT PROJECT REPORTING SUMMARY
| Predevelopment |  |  |  |  | Construction | Operations
Project | Feasibility | RPC Approval | Due Diligence | Financing | Closing | Construction | C. of O. | 100% Occupancy | Cost Cert | 8609
PROJECTS IN OPERATIONS
Englewood | ü | ü | ü | ü | ü | ü | ü | ü
Developer: Holler |  |  |  |  | 2008-12-01 |  | 2010-08-01 | 2010-09-01
Net Developer Fee |  |  |  |  | 360000
Final draw submitted; vendors with outstanding claims are going through the bonding company for funding; working through warranty issues with roof and glass; working on final reconciliation and escrow closeout
Countryside Senior Apts | ü | ü | ü | ü | ü | ü | ü | ü | ü
Developer: Reyes |  |  |  |  | 2010-10-01 |  | 2010-11-01 | 2011-06-01
Net Developer Fee |  |  |  |  | 204386 |  | 190761 |  | 192403 | 540000
IFF converted loan to perm and draw #20 submitted with final developer fee in December 2011
Johnston Center | ü | ü | ü | ü | ü | ü | ü | ü | ü
Developer: Lyon |  |  |  |  | 2009-11-01 |  | 2010-12-01 | 2011-05-01 | 2011-12-01
Net Developer Fee |  |  |  |  | 426000 |  | 334557 |  | 434799 | 307201
Third capital installment submitted and approved; cost cert finalized
Roseland Place | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü
Developer: Reyes |  |  |  |  | 2009-11-01 |  | 2010-11-01 | 2011-07-01
Net Developer Fee |  |  |  |  | 356391 |  |  |  | 56392 | 287786
2nd installment of $56,392 received in December 2011; 4th and 5th installment to be received by 2nd Qtr of 2012
PROJECTS IN CONSTRUCTION IN CURRENT YEAR
Grayslake Senior | ü | ü | ü | ü | ü | ü
Developer: Reyes |  |  |  |  | 2011-11-02 | 2011-11-01 | 2012-11-01
Net Developer Fee |  |  |  |  | 445719 |  | 59948.8
Pullman Wheelworks | ü | ü | ü | ü | ü | ü
Developer: Brace
Net Developer Fee |  |  |  |  | 275000
PROJECTS CLOSING IN CURRENT YEAR
Sterling Park | ü | ü | ü
Developer: Angelini/Reyes |  |  |  |  | 2012-11-01 | 2012-12-01 | 2014-12-01
Net Developer Fee |  |  |  |  | 375000
NOTES
Keating | ü | ü | ü
Developer: Brace |  |  |  |  | 2012-12-01 | 2012-12-01 | 2014-09-01
Net Developer Fee |  |  |  |  | 485341
NOTES:
Kankakee | ü | ü | ü
Developer: Reyes |  |  |  |  | 2013-10-01 | 2013-10-01 | 2014-10-01
Net Developer Fee |  |  |  |  | 226256
Submitted tax credit application to IHDA in December 2011
15 Year Refi Uptown | ü | ü | ü
Developer: Angelini/Blakley |  |  |  |  | 2012-12-01 | 2013-01-01 | 2014-04-01
Net Developer Fee |  |  |  |  | 166666.5
NOTES
Danville VA Hospital | ü | ü | UNDERWAY | UNDERWAY
Developer: Lyon |  |  |  |  | 2012-12-01 | 2013-01-01 | 2013-12-31
Net Developer Fee |  |  |  |  | 162890.5
NOTES: Due to changes in the 2010 QAP there will be no TC application in 2010. Anticipated a 202 application of VA partnership to occur in 2010 with a closing in 2011; need to follow up and meeting with Mike Brown of Provena
PROJECTS UNDER DUE DILIGENCE
26th & Kostner (all other Phases) | ü | DONE | UNDERWAY
Developer: Brace
NOTE: Future Phases | Future phases
5th Ward Senior Project | ü | ü
Developer: Lyon
NOTE: Site control obtained; WHEDA TC application denied due to higher than HUD permitted costs; redesign of building underway to meet these threshold requirements
New City of Milw/USBank Site | UNDERWAY
Developer: Lyon
GC:
NOTE: Project advancing toward a 2011 application with per unit constraints of 2011 QAP
PROJECTS UNDER FEASIBILITY
Childrens Memorial Hospital site in Chicago (Lincoln Park) | UNDERWAY
Developer: TBD
NOTE: McCaffery Interests has been selected as the developer by CMH; MHI has had mtgs with prinipcals and submitted an MOU in Feb.
PROJECTS UNDER REVIEW
Johnston Center 2 | UNDERWAY
Developer: Lyon
NOTE: Meetings underway with church that owns parcel; anticipated to be a part of 2011 TC application
Note on A26: mangelini: This should be moved to active projects section.
Note on A30: mangelini: This should be moved to active projects section.
Note on A55: mangelini: This should be moved up to the active projects section.

## 26th & Kostner
26th & Kostner/Keating
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 4%
| Location | Chicago |  |  | Financing - 2nd |  | Local: City/County Funding
| Construction Type | Adaptive/ Rehab |  |  | Financing - 3rd |  | Local: City/County Funding
| Number of Units | 125 |  |  | Financing - 4th |  | Local: City/County Funding
| Population Served | Family |  |  | Total Development Costs |  | 52200000
|  | Workforce |  |  | Tax Credit Investor |  | TBD
|  | Vets |  |  | Date Tax Credit Awarded |  | Self Generated at Closing
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 17540000
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 15786000
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1754000
[5 empty] | Gross Developer Fee |  | 5176969 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 3882726.75
[5 empty] | Deferred Developer Fee |  | 1294242.25
CURRENT STATUS
| Development Stage | Prospect |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2012-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2012-12-01 |  |  | 2012 Net Developer Fee Forecast |  | 485341
| End of Construction | 2014-09-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | 26th & Kostner/Keating
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD | Confirm volume cap; City Council: PD amendment process - Feb-Sep 2012
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD | Submit tax credit app: Mar 2012
| Public Financing Applications | TBD | TBD | CHA: negotations and internal loan approval Mar 2012; TX CR investor selection - April 2012 & term sheet Jun 2012; HUD - select HUD mortgagee Apr 2012, MAP Processing Jun-Sep 2012, firm commit: Sep 2012; AHP: submit app Mar-Jul 2012
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2012-12-15 | TBD
| Construction Start | 2012-12-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | 26th & Kostner/Keating
| LOCATION OF PROJECT: |  |  |  | Chicago
LEAD DEVELOPER
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | 2012-02-29 | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | 2012-03-30 | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | 2012-02-29 | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | 2012-04-30 | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | 2012-06-30 | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | 2012-04-01 | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2012-12-15 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2012-12-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Countryside
Countryside Senior Apts
L Reyes
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Senior |  |  | Primary Financing |  | LIHTC - 9%
| Location | Countryside |  |  | Financing - 2nd |  | Local: City/County Funding
| Construction Type | New Construction |  |  | Financing - 3rd |  | Grant Funding - Public or Private
| Number of Units | 70 |  |  | Financing - 4th |  | N/A
| Population Served | Senior |  |  | Total Development Costs |  | 16101522
|  | Senior - Independent |  |  | Tax Credit Investor |  | B of A
|  | N/A |  |  | Date Tax Credit Awarded |  | 2009
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 10908330
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 8104760
| Funding Source | Property Operations |  |  | Annual Tax Credit Award |  | 1090833
[5 empty] | Gross Developer Fee |  | 1129550 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1129550
[5 empty] | Deferred Developer Fee |  | 0
CURRENT STATUS
| Development Stage | Operations - Sub Phase Close Out |  |  | Percent Complete |  | 100%
| Date of Deal Close | 2009-09-01 |  |  | Developer Fee Received To Date |  | 587549.5
| Start of Construction | 2009-09-01 |  |  | 2012 Net Developer Fee Forecast |  | 405000
| End of Construction | 2010-09-01
UPCOMING TASKS
- Need to determine final calculation of dev fee to be received based on downward adjuster - what portion becomes deferred fee to be received in later years from cash flow? - See "Countryside Cap Installments" worksheet for required items
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Countryside Senior Apts
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2009-09-01 | 2009-09-01
| Construction Start | 2009-09-01 | 2009-09-01
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Countryside Senior Apts
| LOCATION OF PROJECT: |  |  |  | Countryside
| LEAD DEVELOPER |  |  |  | L Reyes
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2009-09-01 | 2009-09-01
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2009-09-01 | 2009-09-01
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Countryside Cap Installments
Countryside |  |  | GROSS | CONT. | NET
2012 Developer Fee |  |  | 540000 | 25% | 405000
Countryside LPA -- Section 4.8
Conditions Precedent to Final Installment - May not be paid before April 1, 2012
| a. | All conditions precedent to prior installments have been satisfied
| b. | No default or Event of Default has occurred
| c. | LP has received the 8609
| d. | LP has received Accountant's audited certificate determining final credit amount and any adjustments to LP Cap Contributions
| e. | LP has received estoppel letter from lender of MHL loan, dated not more than 30 days prior to final installment payment date
| i. | Seven days prior to final installment payment date, GP has delivered GP installment certificate to LP
| j. | All of the following documents have been delivered (Exhibit L)
- evidence that housing credits of $1,090,833 per annum have been issued by housing agency
- title insurance date down report covering period through final installment payment date, which discloses no liens or encumberances
- Copies of operating statements and rent rolls, certified as true and correct by GP
- Lenders estoppel cert from lender of MHL loan, dated as of final installment payment date
- If requested by LP, update to the tax counsel opinion on any material tax changes since initial installment
- If requested by LP, update opinion of legal counsel to the partnership, GP or GP affiliate
- If requested by LP, certificate showing (a) itemized costs of the project (b) eligible housing credit basis (c) housing credit percentage (d) qualified rehab expenditures of the project (e) calculation of any applicable adjustments in LP capital contribution
- Filed first year tax return of the partnership, including K1 for LP
- Financial statements of GP, dated no earlier that 60 days prior to final installment payment date
- GP has delivered an executed Property Manager Installment Certificate dated as of conversion Installment Payment Date

## Grayslake
Grayslake Senior
| DEMOGRAPHICS |  |  |  |  | FINANCING
| Project Type |  | Senior |  |  | Primary Financing |  | LIHTC - 9%
| Location |  | Grayslake |  |  | Financing - 2nd |  | AHP
| Construction Type |  | New Construction |  |  | Financing - 3rd |  | Grant Funding - Public or Private
| Number of Units |  | 70 |  |  | Financing - 4th |  | Grant Funding - Public or Private
| Population Served |  | Senior |  |  | Total Development Costs |  | 21400000
|  |  | Senior - Independent |  |  | Tax Credit Investor |  | Enterprise/ JP Morgan
|  |  | Disabled - Chronically Mentally Ill |  |  | Date Tax Credit Awarded |  | 2009
| Property Mgmt Company |  | MHMG |  |  | Total Tax Credit Award |  | 20607000
| Resident Services Type |  | Service Coordination |  |  | Total Tax Credit Equity |  | 19164510
| Funding Source |  | TBD |  |  | Annual Tax Credit Award |  | 2060700
[6 empty] | Gross Developer Fee |  | 2030316 | PLEASE PRINT OUT PAGE AS 2 SIDED
[6 empty] | Net Developer Fee |  | 1522737
[6 empty] | Deferred Developer Fee |  | 507579
CURRENT STATUS
| Development Stage |  | Construction |  |  | Percent Complete |  | 40%
| Date of Deal Close |  | 2011-11-02 |  |  | Developer Fee Received To Date |  | 445719
| Start of Construction |  | 2011-11-01 |  |  | 2012 Net Developer Fee Forecast |  | 59948.8
| End of Construction |  | 2012-11-01
UPCOMING TASKS
- Per the LPA, the 2nd and 3rd capital installments cannot be made until 1/1/13 - MHL is forecasting dev fee to be received in 2012; therefore, need to start negotiations to receive dev fee in 2012 - See "Grayslake Cap Installments" worksheet for required items
| SUMMARY OF TASKS AND DEADLINES |  |  | Grayslake Senior
| Task |  | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed |  | Done | Done
| Request for Project Approval |  | Done | Done
| First Dev Coord Mtg |  | Done | Done
| Tax Credit Applications |  | Done | Done
| Public Financing Applications |  | TBD | TBD
| Financing Complete |  | 2011-11-01 | 2011-11-01
| Due Diligence Complete |  | Done | Done
| PRC Approval |  | Done | Done
| Project Set Up in Denver |  | Done | Done
| Closing |  | 2011-10-15 | 2011-10-31
| Construction Start |  | 2011-10-15 | 2011-11-03
| Project Draw Management Set Up |  | Done | TBD
| Project Completion/PIS/C.O. |  | 2012-11-01 | TBD
| Cost Cert |  | 2013-04-30 | TBD
| Final Draw |  | 2013-02-01 | TBD
| Punch List Complete |  | 2012-10-15 | TBD
| 8609 |  | 2013-04-30 | TBD
| Turn Over to Asset Mng |  | 2013-04-30 | TBD
| 2nd and 3rd Capital Installments | Click here for list of requirements
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  |  | Grayslake Senior
| LOCATION OF PROJECT: |  |  |  |  | Grayslake
| LEAD DEVELOPER |  |  |  |  | 0
| BUSINESS PLAN ACTIVITY |  |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  |  | Done | Done
| Photos |  |  |  |  | Done | Done
| Preliminary Pro Forma |  |  |  |  | Done | Done
| Proposed Site Control Details |  |  |  |  | Done | Done
| Executed MOU with Seller |  |  |  |  | Done | Done
| Existing Seller Reports |  |  |  |  | Done | Done
| Preliminary Site Program |  |  |  |  | Done | Done
Feasibility Period LOC
| LOC setup and modification |  |  |  |  | Done | Done
| Check Requests |  |  |  |  | Done | Done
| LOC Log |  |  |  |  | Done | Done
| Cost Coding of all expenses |  |  |  |  | Done | Done
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  |  | Done | Done
| Political Acceptance of Project |  |  |  |  | Done | Done
| Available Subsidies |  |  |  |  | Done | Done
| Preliminary Neighborhood Scan |  |  |  |  | Done | Done
| Environmental Issues |  |  |  |  | Done | Done
| Site Construction Issues |  |  |  |  | Done | Done
| Identify Primary Financing Program |  |  |  |  | Done | Done
| Preliminary Line of Credit for Feasibility Stage |  |  |  |  | Done | Done
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  |  | Done | Done
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  |  | Done | Done
REQUEST FOR PROJECT CONCEPT APPROVAL | [5 empty] | Done | Done
1st PROJECT TEAM COORDINATING MEETING | [5 empty] | Done | Done
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  |  | Done | Done
| 9% LIHTC |  |  |  |  | Done | Done
| 4% Bond |  |  |  |  | NA | NA
| TAX CREDIT APPS COMPLETE |  |  |  |  | Done | Done
| HUD |  |  |  |  | NA | NA
| HOME/CDBG Funds |  |  |  |  | NA | NA
| Trust Funds |  |  |  |  | NA | NA
| FHLB/AHP |  |  |  |  | 2012-04-03 | TBD
| Grants |  |  |  |  | NA | NA
| Operating Subsidy |  |  |  |  | 2012-09-01 | TBD
| CHA Financing |  |  |  |  | NA | NA
| PUBLIC FINANCING APPS COMPLETE |  |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  |  | Done | Done
| Equity |  |  |  |  | Done | Done
| Subsidy/Gap |  |  |  |  | Done | Done
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  |  | Done | Done
| ii. Commitment Letters |  |  |  |  | Done | Done
| iii. Financial Projections |  |  |  |  | Done | Done
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  |  | Done | Done
| ii. Commitment Letters |  |  |  |  | Done | Done
| iii. Financial Projections |  |  |  |  | Done | Done
| iv. Limited Partnership Agreement |  |  |  |  | Done | Done
Subsidy/Gap
| i. Letter Of Intent |  |  |  |  | Done | Done
| ii. Commitment Letters |  |  |  |  | Done | Done
| FINANCING COMPLETE |  |  |  |  | 2011-11-01 | 2011-11-01
PROJECT DUE DILIGENCE
| Photos |  |  |  |  | Done | Done
| Checklists, Timelines & Updates |  |  |  |  | Done | Done
| Due Diligence/Closing Period LOC |  |  |  |  | Done | Done
| LOC setup and modification |  |  |  |  | Done | Done
| Physical/Capital Needs Assessment |  |  |  |  | Done | Done
| Market Study |  |  |  |  | Done | Done
| Environmental Reports |  |  |  |  | Done | Done
| Initial Report |  |  |  |  | Done | Done
| Phase I |  |  |  |  | Done | Done
| Phase II |  |  |  |  | Done | Done
| Appraisal |  |  |  |  | Done | Done
| Survey |  |  |  |  | Done | Done
| Existing |  |  |  |  | Done | Done
| As Built |  |  |  |  | Done | Done
| Municipal Review Process |  |  |  |  | Done | Done
| Zoning |  |  |  |  | Done | Done
| Design |  |  |  |  | Done | Done
| Neighborhood Review/Approval Meetings |  |  |  |  | Done | Done
| Subsidies |  |  |  |  | Done | Done
| TIF |  |  |  |  | Done | Done
| Development Team |  |  |  |  | Done | Done
| Architect/Structural |  |  |  |  | Done | Done
| Engineers |  |  |  |  | Done | Done
| MEP |  |  |  |  | Done | Done
| Energy Modeling/LEEDS/Commissioning |  |  |  |  | Done | Done
| Civil |  |  |  |  | Done | Done
| Construction Manager/General Contractor |  |  |  |  | Done | Done
| Owners Rep |  |  |  |  | Done | Done
| Architectural |  |  |  |  | Done | Done
| Timeline |  |  |  |  | Done | Done
| Schematic Design |  |  |  |  | Done | Done
| renderings |  |  |  |  | Done | Done
| drawings |  |  |  |  | Done | Done
| Design Development |  |  |  |  | Done | Done
| renderings |  |  |  |  | Done | Done
| drawings |  |  |  |  | Done | Done
| Construction Drawings |  |  |  |  | Done | Done
| renderings |  |  |  |  | Done | Done
| drawings |  |  |  |  | Done | Done
| Historic TC Process |  |  |  |  | Done | Done
| Part I submittal |  |  |  |  | Done | Done
| Part II submittal |  |  |  |  | Done | Done
| NPS approval |  |  |  |  | Done | Done
| Part III Certification submittal |  |  |  |  | Done | Done
| Construction Manager/General Contractor |  |  |  |  | Done | Done
| Internal Project Schedule |  |  |  |  | Done | Done
| Cost Estimating |  |  |  |  | Done | Done
| GMP |  |  |  |  | Done | Done
| Contracting |  |  |  |  | Done | Done
| Sustainable Development |  |  |  |  | Done | Done
| Furniture |  |  |  |  | Done | Done
| Relocation |  |  |  |  | Done | Done
| Permit documents |  |  |  |  | Done | Done
| Documentation Requirements for Closing Items |  |  |  |  | Done | Done
| Organizational Documents |  |  |  |  | Done | Done
| LP Formation Documents |  |  |  |  | Done | Done
| GP Formation Documents |  |  |  |  | Done | Done
| JV Formation Documents |  |  |  |  | Done | Done
| Site Control |  |  |  |  | Done | Done
| Standard Agreements |  |  |  |  | Done | Done
| Management |  |  |  |  | Done | Done
| Marketing |  |  |  |  | Done | Done
| DUE DILIGENCE COMPLETE |  |  |  |  | Done | Done
2nd PROJECT TEAM COORDINATING MEETING | [5 empty] | Done | Done
REQUEST FOR PROJECT APPROVAL | [5 empty] | Done | Done
| Detailed LOC to get through closing |  |  |  |  | Done | Done
10% Test | [5 empty] | Done | Done
PRE CLOSING MEETINGS
| Closing Team |  |  |  |  | Done | Done
| Project Specific Closing Checklist |  |  |  |  | Done | Done
| Attorney |  |  |  |  | Done | Done
| Investors |  |  |  |  | Done | Done
| Lender 1 |  |  |  |  | Done | Done
| Debt (residential) |  |  |  |  | Done | Done
| Debt (commercial) |  |  |  |  | Done | Done
| Equity (LIHTC/HTC) |  |  |  |  | Done | Done
| Equity (NMTC) |  |  |  |  | Done | Done
| Subsidy/Gap |  |  |  |  | Done | Done
Lender 0 | Lender 2 |  |  |  |  | Done | Done
Pre Closing Meeting with Denver
| Legal |  |  |  |  | Done | Done
| Treasury |  |  |  |  | Done | Done
| Accounting |  |  |  |  | Done | Done
| Compliance |  |  |  |  | Done | Done
| Construction |  |  |  |  | Done | Done
CLOSING
| Estimated Closing Date |  |  |  |  | 2011-10-15 | 2011-10-31
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  |  | Done | Done
| Delivery of Documents to Denver |  |  |  |  | Done | Done
| Set up of Acccounting Items |  |  |  |  | Done | Done
| PROJECT SETUP IN DENVER |  |  |  |  | Done | Done
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  |  | 2011-10-15 | 2011-11-03
| Owner's Rep Duties and Contract |  |  |  |  | Done | Done
| Draw Mng Set Up Prior to Draw 2 |  |  |  |  | Done | TBD
| Review of Budget and Schedule |  |  |  |  | Done | Done
| MHI Construction VP Site Visits |  |  |  |  | NA | NA
| Site Visits for Monthly Draw Review |  |  |  |  | Done | Done
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  |  | Done | Done
| Timeline of Major Activities for MSC; RS; AM |  |  |  |  | Done | Done
| Quarterly Dev Coordinating Meetings |  |  |  |  | Done | Done
| Update and Reconcile Activities Timeline |  |  |  |  | Done | Done
| Quarterly Dev Coordinating Meetings |  |  |  |  | Done | Done
| Update and Reconcile Activities Timeline |  |  |  |  | Done | Done
| Quarterly Dev Coordinating Meetings |  |  |  |  | Done | Done
| Update and Reconcile Activities Timeline |  |  |  |  | Done | Done
| Quarterly Dev Coordinating Meetings |  |  |  |  | Done | Done
| Update and Reconcile Activities Timeline |  |  |  |  | Done | Done
| Quarterly Dev Coordinating Meetings |  |  |  |  | Done | Done
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  |  | Done | Done
| Certificate of Occupancy/PIS |  |  |  |  | 2012-11-01 | TBD
| Cost Certification |  |  |  |  | 2013-04-30 | TBD
| Dev Fee Installment Payment Conditions |  |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  |  | Done | Done
Owners Sworn Statement | Owners Sworn Statement |  |  |  |  | Done | Done
Invoices | Invoices |  |  |  |  | Done | Done
Sources Statement | Sources Statement |  |  |  |  | Done | Done
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  |  | Done | Done
Internal Reconciliation | Internal Reconciliation |  |  |  |  | Done | Done
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  |  | TBD | TBD
| Invoices |  |  |  |  | TBD | TBD
| Sources Statement |  |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  |  | 2013-02-01 | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  |  | 2012-10-15 | TBD
Outstanding Items Files
| Equity |  |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  |  | NA | TBD
| Grants |  |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  |  | Done | TBD
| Document Deliverables |  |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  |  | 2012-11-01 | TBD
| Guarantees |  |  |  |  | 2012-11-01 | TBD
| Closeout Manual |  |  |  |  | 2012-11-01 | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  |  | 2013-04-30 | TBD
| Transfer of Project to Asset Management |  |  |  |  | 2013-04-30 | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Grayslake Cap Installments
Grayslake |  |  | GROSS | CONT. | NET
2012 Developer Fee |  |  | 599488 | 50% | 299744
Grayslake LPA -- Exhibit A
2nd Capital Installment - NO SOONER THAN JANUARY 1, 2013
|  | Dev Fee | 297146
| a. | Completion Date
| b. | Receipt and approval by LP of draft Cost Cert prepared by the accountants
| c. | Receipt and approval of final release of lien from GC
| d. | Receipt by LP of insurance binders
| e. | Receipt of updated title
| f. | Receipt and approval by LP an as-built ALTA survey
| g. | Evidence that as built plans are approced by the architect
| h. | Satisfactory radon testing
| i. | Receipt and approval by LP an updated source and use that shows partnership will have sufficient funds for loan conversion
| j. | Receipt and approval by the LP of Section 8 commitment
| k. | Receipt and approval by LP that DCEO loan has been funded in full
| l. | Receipt and approval by LP of the extended use agreement
| m. | Completed 10% test files with the authority along with Accountant's certification
| n. | All appropriate reports required in Section 13.03 of the LPA
| o. | Satisfaction of all prior Capital Contributions
3rd Capital Installment - NO SOONER THAN JANUARY 1, 2013
|  | Dev Fee | 302342
| a. | Receipt and approval by LP of cost certification certified by the Accountant - eligible basis, matching souce and use, credit calcs
| b. | Receipt and approval by LP of tax parcel endorsement to the Title Policy and vacation of cul-de-sac
| c. | All appropriate reports required in Section 13.03 of the LPA
| d. | Satisfaction of all prior Capital Contributions

## MKE - Johnston Center
Milwaukee - Johnston Center
D Lyon
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Special Needs (PSH) |  |  | Primary Financing |  | LIHTC - 9%
| Location | Milwaukee |  |  | Financing - 2nd |  | TCAP
| Construction Type | Adaptive/ Rehab |  |  | Financing - 3rd |  | AHP
| Number of Units | 91 |  |  | Financing - 4th |  | Local: City/County Funding
| Population Served | Special Needs (PSH) |  |  | Total Development Costs |  | 13848000
|  | Homeless |  |  | Tax Credit Investor |  | US Bank
|  | Dual Diagnosis |  |  | Date Tax Credit Awarded |  | 2009
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 13750000
| Resident Services Type | Case Management - 3rd party |  |  | Total Tax Credit Equity |  | 9486600
| Funding Source | Government Contracts |  |  | Annual Tax Credit Award |  | 1375000
[5 empty] | Gross Developer Fee |  | 1436566.7356 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1436566.7356
[5 empty] | Deferred Developer Fee |  | 0
CURRENT STATUS
| Development Stage | Operations - Sub Phase Close Out |  |  | Percent Complete |  | 100%
| Date of Deal Close | 2009-12-01 |  |  | Developer Fee Received To Date |  | 1130629.9823
| Start of Construction | 2009-11-01 |  |  | 2012 Net Developer Fee Forecast |  | 307201
| End of Construction | 2010-10-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Milwaukee - Johnston Center
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | 2008-03-25 | 2008-03-25
| Request for Project Approval | 2008-04-18 | 2008-04-18
| First Dev Coord Mtg | 2009-04-01 | 2009-04-01
| Tax Credit Applications | 2009-02-02 | 2009-02-02
| Public Financing Applications | 2010-09-01 | 2010-09-01
| Financing Complete | 2010-12-01 | 2010-12-01
| Due Diligence Complete | 2009-10-01 | 2009-10-01
| PRC Approval | 2009-07-31 | 2009-07-31
| Project Set Up in Denver | 2010-01-01 | 2010-01-01
| Closing | 2009-12-22 | 2009-12-22
| Construction Start | 2009-10-08 | 2009-10-08
| Project Draw Management Set Up | 2009-10-01 | 2009-10-01
| Project Completion/PIS/C.O. | 2010-12-01 | TBD
| Cost Cert | 2011-01-01 | TBD
| Final Draw | 2011-01-01 | TBD
| Punch List Complete | 2010-12-31 | TBD
| 8609 | 2011-04-01 | TBD
| Turn Over to Asset Mng | 2011-05-01 | TBD | Final capital installment to be received in March 2012; turnover will occur thereafter
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Milwaukee - Johnston Center
| LOCATION OF PROJECT: |  |  |  | Milwaukee
| LEAD DEVELOPER |  |  |  | D Lyon
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | 2008-01-15 | 2008-01-15
| Photos |  |  |  | 2008-01-15 | 2008-01-15
| Preliminary Pro Forma |  |  |  | 2008-01-15 | 2008-01-15
| Proposed Site Control Details |  |  |  | 2008-01-15 | 2008-01-15
| Executed MOU with Seller |  |  |  | 2008-01-15 | 2010-02-17
| Existing Seller Reports |  |  |  | 2008-01-15 | 2008-01-15
| Preliminary Site Program |  |  |  | 2008-01-15 | 2008-01-15
Feasibility Period LOC
| LOC setup and modification |  |  |  | 2008-01-15 | 2008-01-15
| Check Requests |  |  |  | 2008-01-15 | 2008-01-15
| LOC Log |  |  |  | 2008-01-15 | 2008-01-15
| Cost Coding of all expenses |  |  |  | 2008-01-15 | 2008-01-15
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | 2008-01-15 | 2008-01-15
| Political Acceptance of Project |  |  |  | 2008-01-15 | 2008-01-15
| Available Subsidies |  |  |  | 2008-01-15 | 2008-01-15
| Preliminary Neighborhood Scan |  |  |  | 2008-01-15 | 2008-01-15
| Environmental Issues |  |  |  | 2008-01-15 | 2008-01-15
| Site Construction Issues |  |  |  | 2008-01-15 | 2008-01-15
| Identify Primary Financing Program |  |  |  | 2008-01-15 | 2008-01-15
| Preliminary Line of Credit for Feasibility Stage |  |  |  | 2008-01-15 | 2008-01-15
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | 2008-01-15 | 2008-01-15
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | 2008-03-25 | 2008-03-25
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | 2008-04-18 | 2008-04-18
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | 2009-04-01 | 2009-04-01
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | N/A | N/A
| 9% LIHTC |  |  |  | 2009-02-02 | 2009-02-02
| 4% Bond |  |  |  | N/A | N/A
| TAX CREDIT APPS COMPLETE |  |  |  | 2009-02-02 | 2009-02-02
| HUD |  |  |  | N/A | N/A
| HOME/CDBG Funds |  |  |  | N/A | N/A
| Trust Funds |  |  |  | 2008-01-01 | 2008-01-01
| FHLB/AHP |  |  |  | 2010-09-01 | TBD
| Grants |  |  |  | 2008-01-01 | 2008-01-01
| Operating Subsidy |  |  |  | 2010-09-01 | 2010-09-01
| CHA Financing |  |  |  | N/A | N/A
| PUBLIC FINANCING APPS COMPLETE |  |  |  | 2010-09-01 | 2010-09-01
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | 2009-01-01 | 2009-01-01
| Equity |  |  |  | 2009-01-01 | 2009-01-01
| Subsidy/Gap |  |  |  | 2009-01-01 | 2009-01-01
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | 2009-02-01 | 2009-02-01
| ii. Commitment Letters |  |  |  | 2009-08-01 | 2009-08-01
| iii. Financial Projections |  |  |  | 2009-12-01 | 2009-12-01
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | 2009-02-01 | 2009-02-01
| ii. Commitment Letters |  |  |  | 2009-08-01 | 2009-08-01
| iii. Financial Projections |  |  |  | 2009-12-01 | 2009-12-01
| iv. Limited Partnership Agreement |  |  |  | 2009-12-01 | 2009-12-01
Subsidy/Gap
| i. Letter Of Intent |  |  |  | 2010-12-01 | TBD
| ii. Commitment Letters |  |  |  | 2010-12-01 | TBD
| FINANCING COMPLETE |  |  |  | 2010-12-01 | 2010-12-01
PROJECT DUE DILIGENCE
| Photos |  |  |  | 2008-01-01 | 2008-01-01
| Checklists, Timelines & Updates |  |  |  | 2010-03-26 | 2010-03-26
Due Diligence/Closing Period LOC
| LOC setup and modification |  |  |  | 2009-07-01 | 2009-07-01
| Physical/Capital Needs Assessment |  |  |  | N/A | N/A
| Market Study |  |  |  | 2009-01-01 | 2009-01-01
Environmental Reports
| Initial Report |  |  |  | 2008-01-01 | 2008-01-01
| Phase I |  |  |  | 2009-04-01 | 2009-04-01
| Phase II |  |  |  | 2009-05-01 | 2009-05-01
Appraisal
Survey
| Existing |  |  |  | 2009-07-01 | 2009-07-01
| As Built |  |  |  | TBD | TBD
Municipal Review Process
| Zoning |  |  |  | 2009-05-01 | 2009-05-01
| Design |  |  |  | 2009-05-01 | 2009-05-01
| Neighborhood Review/Approval Meetings |  |  |  | 2008-01-01 | 2008-01-01
| Subsidies |  |  |  | 2009-05-01 | 2009-05-01
| TIF |  |  |  | N/A | N/A
Development Team
| Architect/Structural |  |  |  | 2009-01-01 | 2009-01-01
Engineers
| MEP |  |  |  | 2009-01-01 | 2009-01-01
| Energy Modeling/LEEDS/Commissioning |  |  |  | 2009-01-01 | 2009-01-01
| Civil |  |  |  | 2009-01-01 | 2009-01-01
| Construction Manager/General Contractor |  |  |  | 2009-01-01 | 2009-01-01
| Owners Rep |  |  |  | 2010-09-01 | 2010-09-01
Architectural
| Timeline |  |  |  | 2008-01-01 | 2008-01-01
| Schematic Design |  |  |  | 2008-01-01 | 2008-01-01
| renderings |  |  |  | 2008-01-01 | 2008-01-01
| drawings |  |  |  | 2008-01-01 | 2008-01-01
Design Development
| renderings |  |  |  | 2008-01-01 | 2008-01-01
| drawings |  |  |  | 2008-01-01 | 2008-01-01
Construction Drawings
| renderings |  |  |  | 2009-07-01 | 2009-07-01
| drawings |  |  |  | 2009-07-01 | 2009-07-01
Historic TC Process
| Part I submittal |  |  |  | N/A | N/A
| Part II submittal |  |  |  | N/A | N/A
| NPS approval |  |  |  | N/A | N/A
| Part III Certification submittal |  |  |  | N/A | N/A
Construction Manager/General Contractor
| Internal Project Schedule |  |  |  | 2009-04-15 | 2009-04-15
| Cost Estimating |  |  |  | 2009-01-01 | 2009-01-01
| GMP |  |  |  | 2009-09-01 | 2009-09-01
| Contracting |  |  |  | 2009-10-01 | 2009-10-01
| Sustainable Development |  |  |  |  | 0
| Furniture |  |  |  | 2010-05-01 | TBD
| Relocation |  |  |  | N/A | N/A
| Permit documents |  |  |  | 2009-07-01 | 2009-07-01
Documentation Requirements for Closing Items
| Organizational Documents |  |  |  | 2009-10-01 | 2009-10-01
| LP Formation Documents |  |  |  | 2009-10-01 | 2009-10-01
| GP Formation Documents |  |  |  | 2009-10-01 | 2009-10-01
| JV Formation Documents |  |  |  | N/A | N/A
| Site Control |  |  |  | 2008-12-31 | 2008-12-31
Standard Agreements
| Management |  |  |  | 2009-09-01 | 2009-09-01
| Marketing |  |  |  | 2009-09-01 | 2009-09-01
| DUE DILIGENCE COMPLETE |  |  |  | 2009-10-01 | 2009-10-01
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | 2009-07-01 | 2009-07-01
REQUEST FOR PROJECT APPROVAL |  |  |  |  | 2009-07-31 | 2009-07-31
| Detailed LOC to get through closing |  |  |  | 2009-07-31 | 2009-07-31
10% Test |  |  |  |  | 2009-10-01 | 2009-10-01
PRE CLOSING MEETINGS
| Closing Team |  |  |  | 2009-08-31 | 2009-08-31
| Project Specific Closing Checklist |  |  |  | 2009-09-30 | 2009-09-30
| Attorney |  |  |  | 2009-09-30 | 2009-09-30
| Investors |  |  |  | 2009-09-30 | 2009-09-30
Lender 1
| Debt (residential) |  |  |  | 2009-09-30 | 2009-09-30
| Debt (commercial) |  |  |  | N/A | N/A
| Equity (LIHTC/HTC) |  |  |  | 2009-09-30 | 2009-09-30
| Equity (NMTC) |  |  |  | N/A | N/A
| Subsidy/Gap |  |  |  | 2009-09-30 | 2009-09-30
Lender 0 | Lender 2 |  |  |  | N/A | N/A
Pre Closing Meeting with Denver
| Legal |  |  |  | 2009-11-01 | 2009-11-01
| Treasury |  |  |  | 2009-11-01 | 2009-11-01
| Accounting |  |  |  | 2009-11-01 | 2009-11-01
| Compliance |  |  |  | 2009-11-01 | 2009-11-01
| Construction |  |  |  | 2009-11-01 | 2009-11-01
CLOSING
| Estimated Closing Date |  |  |  | 2009-12-22 | 2009-12-22
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | 2009-12-01 | 2009-12-01
| Delivery of Documents to Denver |  |  |  | 2010-01-01 | 2010-01-01
| Set up of Acccounting Items |  |  |  | 2010-01-01 | 2010-01-01
| PROJECT SETUP IN DENVER |  |  |  | 2010-01-01 | 2010-01-01
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2009-10-08 | 2009-10-08
| Owner's Rep Duties and Contract |  |  |  | 2009-09-01 | 2009-09-01
| Draw Mng Set Up Prior to Draw 2 |  |  |  | 2009-10-01 | 2009-10-01
| Review of Budget and Schedule |  |  |  | 2009-09-01 | 2009-09-01
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | Monthly | Monthly
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | 2009-04-01 | 2009-04-01
| Timeline of Major Activities for MSC; RS; AM |  |  |  | 2009-04-01 | 2009-04-01
| Quarterly Dev Coordinating Meetings |  |  |  | 2009-07-01 | 2009-07-01
| Update and Reconcile Activities Timeline |  |  |  | 2009-07-01 | 2009-07-01
| Quarterly Dev Coordinating Meetings |  |  |  | 2010-04-23 | 2010-04-23
| Update and Reconcile Activities Timeline |  |  |  | 2010-04-23 | 2010-04-23
| Quarterly Dev Coordinating Meetings |  |  |  | 2010-07-01 | 2010-07-01
| Update and Reconcile Activities Timeline |  |  |  | 2010-07-01 | 2010-07-01
| Quarterly Dev Coordinating Meetings |  |  |  | 2010-10-01 | TBD
| Update and Reconcile Activities Timeline |  |  |  | 2010-10-01 | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | 2010-12-01 | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | 2010-12-01 | TBD
| Certificate of Occupancy/PIS |  |  |  | 2010-12-01 | TBD
| Cost Certification |  |  |  | 2011-01-01 | TBD
| Dev Fee Installment Payment Conditions |  |  |  | 2011-03-02 | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | Monthly | Monthly
Owners Sworn Statement | Owners Sworn Statement |  |  |  | Monthly | Monthly
Invoices | Invoices |  |  |  | Monthly | Monthly
Sources Statement | Sources Statement |  |  |  | Monthly | Monthly
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | Monthly | Monthly
Internal Reconciliation | Internal Reconciliation |  |  |  | Monthly | Monthly
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | N/A | TBD
| Owners Sworn Statement |  |  |  | N/A | TBD
| Invoices |  |  |  | N/A | TBD
| Sources Statement |  |  |  | N/A | TBD
| Escrow Disbursement Statement |  |  |  | N/A | TBD
| Internal Reconciliation |  |  |  | N/A | TBD
| FINAL DRAW |  |  |  | 2011-01-01 | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | 2010-12-31 | TBD
Outstanding Items Files
| Equity |  |  |  | 2009-12-31 | TBD
| Historic Part III Certification |  |  |  | N/A | TBD
| Grants |  |  |  | 2009-12-31 | TBD
| Lease Up Schedule |  |  |  | 2009-12-31 | TBD
| Document Deliverables |  |  |  | 2009-12-31 | TBD
As Built
| Warranties |  |  |  | 2009-12-31 | TBD
| Guarantees |  |  |  | 2009-12-31 | TBD
| Closeout Manual |  |  |  | 2009-12-31 | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | 2011-04-01 | TBD
| Transfer of Project to Asset Management |  |  |  | 2011-05-01 | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Pullman
Pullman Wheelworks
L Brace
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 4%
| Location | Chicago |  |  | Financing - 2nd |  | Local: State Funding
| Construction Type | Acquisition/ Rehab |  |  | Financing - 3rd |  | Local: City/County Funding
| Number of Units | 210 |  |  | Financing - 4th |  | Grant Funding - Public or Private
| Population Served | Family |  |  | Total Development Costs |  | 30136151
|  | Workforce |  |  | Tax Credit Investor |  | National Affordable Housing Trust
|  | N/A |  |  | Date Tax Credit Awarded |  | 2011
| Property Mgmt Company | Leasing and Mgmt Corp. |  |  | Total Tax Credit Award |  | 8618590
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 8320580
| Funding Source | Property Operations |  |  | Annual Tax Credit Award |  | 861859
[5 empty] | Gross Developer Fee |  | 2976286 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1100000
[5 empty] | Deferred Developer Fee |  | 1876286
CURRENT STATUS
| Development Stage | Construction |  |  | Percent Complete |  | 5%
| Date of Deal Close | 2011-12-01 |  |  | Developer Fee Received To Date |  | 275000
| Start of Construction | 2011-12-31 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2013-09-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Pullman Wheelworks
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | 2012-12-31 | TBD | AHP: submit to US Bank Mar 2012 award by year end; HOME/CDBG loan: negotiation & internal City approval by Jun 2012, full council approval by Sep 2012; DCEO: negotiations with CNI with approval by Dec 2012
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2011-12-15 | 2011-12-15
| Construction Start | 2011-12-31 | 2011-12-31
| Project Draw Management Set Up | 2012-01-15 | 2012-01-15
| Project Completion/PIS/C.O. | 2011-08-31 | 2011-08-31
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Pullman Wheelworks
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | L Brace
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | 2012-06-30 | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | 2012-07-01 | TBD
| Grants |  |  |  | 2012-12-31 | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | 2012-12-31 | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2011-12-15 | 2011-12-15
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | 2012-02-15
| Set up of Acccounting Items |  |  |  | TBD | 2012-02-15
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2011-12-31 | 2011-12-31
| Owner's Rep Duties and Contract |  |  |  | 2012-02-15 | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | 2012-01-15 | 2012-01-15
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | N/A | N/A
| Certificate of Occupancy/PIS |  |  |  | 2011-08-31 | 2011-08-31
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Pullman Cap Installments
Pullman |  |  | GROSS | CONT. | NET | DEVELOPER FEE SCHEDULE
2012 Developer Fee |  |  | 0 | 0% | 0 | Total Development Fee |  | 2976286
| Pullman LPA -- Exhibit A-1 |  |  |  |  | MHL | 67% | 1994111.62
| Second Installment |  |  |  |  | NHT-E | 33% | 982174.38
$4,313,630 - at August 15, 2013
Accrual Schedule
| Third Installment |  |  |  |  | At Closing |  | 30%
|  | $4,006,276 -- Latest of: |  |  |  | At Construction Completion |  | 50%
| a. | Completion date |  |  |  | Receipt of 8609 and Stabilization |  | 20%
| b. | 100% lien free completion of the construction including receipt by LP of evidence of no liens
| c. | Copies of all insurance binders/documents |  |  |  | Development Fee Payout
| d. | Receipt of final cost cert |  |  |  | $715,000 shall be paid upon 1st Installment of the LP
| e. | Final, executed documents of all loans |  |  |  | Capital Contribution - COMPLETE
| f. | Receipt by LP of Radon Report
| g. | December 15, 2013 |  |  |  | $385,000 shall be paid upon the 4th Installment of the LP
Capital Contribution - MHL portion: $257,950
Fourth Installment
|  | $783,327 -- Latest of: |  |  |  | $1,876,286 of the Development Fee shall be deferred and
| a. | Receipt of 8609 |  |  |  | payable from cash flow
| b. | Satisfaction of all conditions to all prior capital contributions
| c. | Receipt of tax returns and financial statements (including K1s)
| d. | Receipt of NFR from IEPA
| e. | Achievement of stabilization date
| f. | Achievement of 100% occupancy
| g. | LP receipt and approval of all TICs and files
| h. | Receipt of Part 3 approval
| i. | If required, followup Radon report detailing all mitigation measures
| j. | Evidence from Accountants that 50% test is satisfied
| k. | April 15, 2014

## Roseland
Roseland Place
L Reyes
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Senior |  |  | Primary Financing |  | HUD 202
| Location | Chicago |  |  | Financing - 2nd |  | LIHTC - 9%
| Construction Type | New Construction |  |  | Financing - 3rd |  | Local: State Funding
| Number of Units | 60 |  |  | Financing - 4th |  | Grant Funding - Public or Private
| Population Served | Senior |  |  | Total Development Costs |  | 17786000
|  | Senior - Independent |  |  | Tax Credit Investor |  | B of A
|  | N/A |  |  | Date Tax Credit Awarded |  | 2009
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 8442046
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 6753638
| Funding Source | Government Contracts |  |  | Annual Tax Credit Award |  | 844204.6
[5 empty] | Gross Developer Fee |  | 700570 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 700570
[5 empty] | Deferred Developer Fee |  | 0
CURRENT STATUS
| Development Stage | Operations - Sub Phase Close Out |  |  | Percent Complete |  | 100%
| Date of Deal Close | 2009-12-01 |  |  | Developer Fee Received To Date |  | 412783.5
| Start of Construction | 2009-12-01 |  |  | 2012 Net Developer Fee Forecast |  | 287786
| End of Construction | 2011-03-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Roseland Place
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2009-12-31 | TBD
| Construction Start | 2009-12-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Roseland Place
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | L Reyes
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2009-12-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2009-12-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Sterling Park
Sterling Park
M Angelini
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 4%
| Location | Chicago |  |  | Financing - 2nd |  | Local: City/County Funding
| Construction Type | Adaptive/ Rehab |  |  | Financing - 3rd |  | Grant Funding - Public or Private
| Number of Units | 181 |  |  | Financing - 4th |  | N/A
| Population Served | Family |  |  | Total Development Costs |  | 45700000
|  | Workforce |  |  | Tax Credit Investor |  | TBD
|  | N/A |  |  | Date Tax Credit Awarded |  | Self Generated at Closing
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 14400310
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 13680294.5
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1440031
[5 empty] | Gross Developer Fee |  | 2718225 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1000000
[5 empty] | Deferred Developer Fee |  | 1718225
CURRENT STATUS
| Development Stage | Development |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2012-11-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2012-12-01 |  |  | 2012 Net Developer Fee Forecast |  | 375000
| End of Construction | 2014-12-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Sterling Park
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD | TX CR: Application not approved by DHED, developing new strategy for financing; AHP: application due Aug 2012
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2012-11-30 | TBD
| Construction Start | 2012-12-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Sterling Park
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | M Angelini
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | 2012-08-30 | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2012-11-30 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2012-12-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## MKE - 5th Ward
5th Ward Senior Project/ Milwaukee
D Lyon
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Senior |  |  | Primary Financing |  | LIHTC - 9%
| Location | Milwaukee |  |  | Financing - 2nd |  | Local: Other
| Construction Type | New Construction |  |  | Financing - 3rd |  | TBD
| Number of Units | 55 |  |  | Financing - 4th |  | N/A
| Population Served | Senior |  |  | Total Development Costs |  | 9500000
|  | Senior - Independent |  |  | Tax Credit Investor |  | TBD
|  | N/A |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 10500000
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 9450000
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1050000
[5 empty] | Gross Developer Fee |  | 889000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 666750
[5 empty] | Deferred Developer Fee |  | 222250
CURRENT STATUS
| Development Stage | Development |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2013-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2014-01-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2015-01-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | 5th Ward Senior Project/ Milwaukee
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | 2010-12-31 | 2010-12-31
| Request for Project Approval | 2012-06-12 | TBD | This will modify original Concept Approval for new structure.
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | 2013-01-01 | TBD
| Public Financing Applications | 2013-01-01 | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-12-01 | 2013-12-01
| Construction Start | TBD | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | 5th Ward Senior Project/ Milwaukee
| LOCATION OF PROJECT: |  |  |  | Milwaukee
| LEAD DEVELOPER |  |  |  | D Lyon
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | 2012-02-15 | 2012-02-15
| Photos |  |  |  | 2012-12-31 | TBD
| Preliminary Pro Forma |  |  |  | 2012-12-31 | TBD
| Proposed Site Control Details |  |  |  | 2012-12-31 | TBD
| Executed MOU with Seller |  |  |  | 2012-12-31 | TBD
| Existing Seller Reports |  |  |  | 2012-12-31 | TBD
| Preliminary Site Program |  |  |  | 2012-12-31 | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | 2012-06-12 | TBD
| Check Requests |  |  |  | 2012-06-12 | TBD
| LOC Log |  |  |  | 2012-06-12 | TBD
| Cost Coding of all expenses |  |  |  | 2012-06-12 | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | 2011-12-31 | 2011-12-31
| Political Acceptance of Project |  |  |  | 2011-12-31 | 2011-12-31
| Available Subsidies |  |  |  | 2011-12-31 | 2011-12-31
| Preliminary Neighborhood Scan |  |  |  | 2011-12-31 | 2011-12-31
| Environmental Issues |  |  |  | 2012-06-12 | TBD
| Site Construction Issues |  |  |  | 2012-06-12 | TBD
| Identify Primary Financing Program |  |  |  | 2012-06-12 | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | 2012-06-12 | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | 2012-06-12 | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | 2010-12-31 | 2010-12-31
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | 2012-06-12 | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | N/A | N/A
| 9% LIHTC |  |  |  | 2013-01-01 | TBD
| 4% Bond |  |  |  | N/A | N/A
| TAX CREDIT APPS COMPLETE |  |  |  | 2013-01-01 | TBD
| HUD |  |  |  | N/A | N/A
| HOME/CDBG Funds |  |  |  | N/A | N/A
| Trust Funds |  |  |  | N/A | N/A
| FHLB/AHP |  |  |  | N/A | N/A
| Grants |  |  |  | N/A | N/A
| Operating Subsidy |  |  |  | N/A | N/A
| CHA Financing |  |  |  | N/A | N/A
| PUBLIC FINANCING APPS COMPLETE |  |  |  | 2013-01-01 | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | 2012-06-01 | TBD
| Equity |  |  |  | 2012-06-01 | TBD
| Subsidy/Gap |  |  |  | 2012-06-01 | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | 2011-12-31 | 2011-12-31
| Checklists, Timelines & Updates |  |  |  | 2011-12-31 | 2011-12-31
Due Diligence/Closing Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
Environmental Reports
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
Appraisal
Survey
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
Municipal Review Process
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
Development Team
| Architect/Structural |  |  |  | TBD | TBD
Engineers
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
Architectural
| Timeline |  |  |  | 2012-06-01 | 2012-06-01
| Schematic Design |  |  |  | 2012-06-01 | 2012-06-01
| renderings |  |  |  | 2012-06-01 | 2012-06-01
| drawings |  |  |  | 2012-06-01 | 2012-06-01
Design Development
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Construction Drawings
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Historic TC Process
| Part I submittal |  |  |  | N/A | N/A
| Part II submittal |  |  |  | N/A | N/A
| NPS approval |  |  |  | N/A | N/A
| Part III Certification submittal |  |  |  | N/A | N/A
Construction Manager/General Contractor
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
Documentation Requirements for Closing Items
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-12-01 | 2013-12-01
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | TBD | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | N/A | N/A
| Owners Sworn Statement |  |  |  | N/A | N/A
| Invoices |  |  |  | N/A | N/A
| Sources Statement |  |  |  | N/A | N/A
| Escrow Disbursement Statement |  |  |  | N/A | N/A
| Internal Reconciliation |  |  |  | N/A | N/A
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## MKE - Greenwich Apts
Milwaukee Greenwich Apartments
D Lyon
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 9%
| Location | Milwaukee |  |  | Financing - 2nd |  | TBD
| Construction Type | New Construction |  |  | Financing - 3rd |  | TBD
| Number of Units | 55 |  |  | Financing - 4th |  | TBD
| Population Served | Family |  |  | Total Development Costs |  | 11000000
|  | Workforce |  |  | Tax Credit Investor |  | TBD
|  | N/A |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 10500000
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 9450000
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1050000
[5 empty] | Gross Developer Fee |  | 1052000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 789000
[5 empty] | Deferred Developer Fee |  | 263000
CURRENT STATUS
| Development Stage | Development |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2013-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2014-01-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2015-01-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Milwaukee Greenwich Apartments
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | 2010-12-31 | 2010-12-31
| Request for Project Approval | 2012-06-12 | TBD | This will modify original concept approval for new structure.
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | 2013-01-01 | TBD
| Public Financing Applications | 2013-01-01 | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-12-01 | 2013-12-01
| Construction Start | TBD | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Milwaukee Greenwich Apartments
| LOCATION OF PROJECT: |  |  |  | Milwaukee
| LEAD DEVELOPER |  |  |  | D Lyon
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | 2012-02-15 | 2012-02-15
| Photos |  |  |  | 2012-12-31 | TBD
| Preliminary Pro Forma |  |  |  | 2012-12-31 | TBD
| Proposed Site Control Details |  |  |  | 2012-12-31 | TBD
| Executed MOU with Seller |  |  |  | 2012-12-31 | TBD
| Existing Seller Reports |  |  |  | 2012-12-31 | TBD
| Preliminary Site Program |  |  |  | 2012-12-31 | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | 2012-06-12 | TBD
| Check Requests |  |  |  | 2012-06-12 | TBD
| LOC Log |  |  |  | 2012-06-12 | TBD
| Cost Coding of all expenses |  |  |  | 2012-06-12 | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | 2011-12-31 | 2011-12-31
| Political Acceptance of Project |  |  |  | 2011-12-31 | 2011-12-31
| Available Subsidies |  |  |  | 2011-12-31 | 2011-12-31
| Preliminary Neighborhood Scan |  |  |  | 2011-12-31 | 2011-12-31
| Environmental Issues |  |  |  | 2012-06-12 | TBD
| Site Construction Issues |  |  |  | 2012-06-12 | TBD
| Identify Primary Financing Program |  |  |  | 2012-06-12 | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | 2012-06-12 | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | 2012-06-12 | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | 2010-12-31 | 2010-12-31
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | 2012-06-12 | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | N/A | N/A
| 9% LIHTC |  |  |  | 2013-01-01 | TBD
| 4% Bond |  |  |  | N/A | N/A
| TAX CREDIT APPS COMPLETE |  |  |  | 2013-01-01 | TBD
| HUD |  |  |  | N/A | N/A
| HOME/CDBG Funds |  |  |  | N/A | N/A
| Trust Funds |  |  |  | N/A | N/A
| FHLB/AHP |  |  |  | N/A | N/A
| Grants |  |  |  | N/A | N/A
| Operating Subsidy |  |  |  | N/A | N/A
| CHA Financing |  |  |  | N/A | N/A
| PUBLIC FINANCING APPS COMPLETE |  |  |  | 2013-01-01 | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | 2012-06-01 | TBD
| Equity |  |  |  | 2012-06-01 | TBD
| Subsidy/Gap |  |  |  | 2012-06-01 | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | 2011-12-31 | 2011-12-31
| Checklists, Timelines & Updates |  |  |  | 2011-12-31 | 2011-12-31
Due Diligence/Closing Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
Environmental Reports
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
Appraisal
Survey
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
Municipal Review Process
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
Development Team
| Architect/Structural |  |  |  | TBD | TBD
Engineers
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
Architectural
| Timeline |  |  |  | 2012-06-01 | 2012-06-01
| Schematic Design |  |  |  | 2012-06-01 | 2012-06-01
| renderings |  |  |  | 2012-06-01 | 2012-06-01
| drawings |  |  |  | 2012-06-01 | 2012-06-01
Design Development
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Construction Drawings
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Historic TC Process
| Part I submittal |  |  |  | N/A | N/A
| Part II submittal |  |  |  | N/A | N/A
| NPS approval |  |  |  | N/A | N/A
| Part III Certification submittal |  |  |  | N/A | N/A
Construction Manager/General Contractor
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
Documentation Requirements for Closing Items
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-12-01 | 2013-12-01
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | TBD | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | N/A | N/A
| Owners Sworn Statement |  |  |  | N/A | N/A
| Invoices |  |  |  | N/A | N/A
| Sources Statement |  |  |  | N/A | N/A
| Escrow Disbursement Statement |  |  |  | N/A | N/A
| Internal Reconciliation |  |  |  | N/A | N/A
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## YMCA Austin
YMCA Austin
L Brace
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Special Needs (PSH) |  |  | Primary Financing |  | LIHTC - 9%
| Location | Chicago |  |  | Financing - 2nd |  | TBD
| Construction Type | New Construction |  |  | Financing - 3rd |  | TBD
| Number of Units | 160 |  |  | Financing - 4th |  | TBD
| Population Served | Special Needs (PSH) |  |  | Total Development Costs |  | 32000000
|  | Homeless |  |  | Tax Credit Investor |  | TBD
|  | Dual Diagnosis |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 24000000
| Resident Services Type | Case Management - In House |  |  | Total Tax Credit Equity |  | 18720000
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 2400000
[5 empty] | Gross Developer Fee |  | 3104000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1000000
[5 empty] | Deferred Developer Fee |  | 2104000
CURRENT STATUS
| Development Stage | Prospect |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2013-10-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2013-10-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2015-04-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | YMCA Austin
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-10-31 | TBD
| Construction Start | 2013-10-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | YMCA Austin
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | L Brace
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-10-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2013-10-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## HWA
Harold Washington Apts
M Angelini
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Special Needs (PSH) |  |  | Primary Financing |  | LIHTC - 4%
| Location | Chicago |  |  | Financing - 2nd |  | Local: City/County Funding
| Construction Type | Refinance/ Rehab |  |  | Financing - 3rd |  | Local: State Funding
| Number of Units | 69 |  |  | Financing - 4th |  | N/A
| Population Served | Special Needs (PSH) |  |  | Total Development Costs |  | 15100000
|  | Homeless |  |  | Tax Credit Investor |  | B of A
|  | Dual Diagnosis |  |  | Date Tax Credit Awarded |  | 2009
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 4638364.6053
| Resident Services Type | Case Management - In House |  |  | Total Tax Credit Equity |  | 3525157.1
| Funding Source | Government Contracts |  |  | Annual Tax Credit Award |  | 463836.4605
[5 empty] | Gross Developer Fee |  | 1757000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 997000
[5 empty] | Deferred Developer Fee |  | 760000
CURRENT STATUS
| Development Stage | Operations - Sub Phase Close Out |  |  | Percent Complete |  | 95%
| Date of Deal Close | 2010-08-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2010-09-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2012-03-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Harold Washington Apts
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2010-08-31 | 2010-08-31
| Construction Start | 2010-09-30 | 2010-09-30
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Harold Washington Apts
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | M Angelini
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2010-08-31 | 2010-08-31
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2010-09-30 | 2010-09-30
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## 850 Eastwood
850 N Eastwood
M Angelini
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 4%
| Location | Chicago |  |  | Financing - 2nd |  | Local: City/County Funding
| Construction Type | Acquisition/ Rehab |  |  | Financing - 3rd |  | Local: State Funding
| Number of Units | 231 |  |  | Financing - 4th |  | N/A
| Population Served | Family |  |  | Total Development Costs |  | 53000000
|  | Workforce |  |  | Tax Credit Investor |  | B of A
|  | N/A |  |  | Date Tax Credit Awarded |  | 2009
| Property Mgmt Company | Leasing & Mgmt Corp. |  |  | Total Tax Credit Award |  | 15528440
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 11801612.9
| Funding Source | Property Operations |  |  | Annual Tax Credit Award |  | 1552844
[5 empty] | Gross Developer Fee |  | 5882000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 3000
[5 empty] | Deferred Developer Fee |  | 5879000
CURRENT STATUS
| Development Stage | Operations - Sub Phase Lease Up |  |  | Percent Complete |  | 95%
| Date of Deal Close | 2010-08-01 |  |  | Developer Fee Received To Date |  | 172500
| Start of Construction | 2010-08-01 |  |  | 2012 Net Developer Fee Forecast |  | 637500
| End of Construction | 2012-03-01
UPCOMING TASKS
- Completion Installment no later than 7-1-11 - Conversion Installment no later than 3/1/12 - Final Installment no later than 4/1/12 - Forecasting $637,500 to be received in 2012 - see "HWA-850 Capital Installments" worksheet for requirements to receive capital installments
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | 850 N Eastwood
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2010-08-30 | 2010-08-30
| Construction Start | 2010-08-30 | 2010-08-30
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | 850 N Eastwood
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | M Angelini
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2010-08-30 | 2010-08-30
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2010-08-30 | 2010-08-30
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## HWA-850 Capital Installments
HWA-850 |  |  | GROSS | CONT. | NET
2012 Developer Fee |  |  | 750000 | 15% | 637500
HWA-850 LPA -- Section 4.06
Conditions Precedent to Completion Installment - May not be paid before July 1, 2011
| a. | All conditions precedent to prior installments have been satisfied
| b. | No default or Event of Default has occurred
| c. | Completion of Construction has been achieved
| d. | Evidence that any environmental remediation, removal or disposal recommended by Phase 1 report or required by law has been remediated
| e. | LP has received Architect's Certificate of Full Completion, subject to punchlist not exceeding $50,000
| f. | LP has received report for Construction Consultant certifying full completion
| g. | LP has received Accountant's certification of Preliminary Credit Amount
| h. | GP has paid LP any amount payable under Section 4.02 "Adjustment of LPs Capital Contribution"
| i. | LP has evidence that National Park Service has approved amendments to Form 10-168b (Part 2)
| j. | LP has received from Architect that the rehabilitation of the project completed through the Completion Installment Payment Date has been built in a manner consistent with National Park Service Form 10-168b (Part 2) and with Historic preservation Certificate Application for State Historic Tax Credits
| k. | LP has satisfactory evidence that the BMIR has been fully funded in accordance with Section 10.04d
| l. | General Partner Installment Certificate has been delivered to LP with respect to Completion Installment
| m. | All of the following documents have been delivered:
- Certificate of Occpuancy (maybe temporary)
- Final lien waiver by each GC
- Receipt of General Contractor's Installment Certificate from each GC
- Title insurance date down endorsement covering the period from initial installment to completion installment
- Update on tax counsel opinion
- Updated opinion of legal counsel if any material changes
- Lenders estoppel cert from the lender of the MHL loan dated as of the completion installment payment date
- Copies of documents in connection with loans not previously delivered to LP
- Evidence of payment of all amounts outstanding under each GC and removal of all liens
- Financial statements of GP and guarantor, dated no earlier than 60 days prior to the Completion Installment Payment Date
- Evidence that all insurance policies are in full force and effect as of Completion Installment Payment Date
- GP has delivered an executed Property Manager Installment Certificate dated as of Completion Installment Payment Date
Conditions Precedent to Conversion Installment - May not be paid before March 1, 2012
| a. | All conditions precedent to prior installments have been satisfied
| b. | No default or Event of Default has occurred
| c. | Project has achieved DSCR on the permanent loans of at least 1.10 for at least three consecutive months
| d. | Certified rent roll that shows at least 90% of the Residential Units are leased and occupied by tenants and at least 90% of the Affordable Residential Units are leased and occupied by qualified low income tenants; leases are in compliance with the Regulatory Agreement and Credit Conditions for a period of three consecutive months
| e. | LP has received evidence, from certified rent roll, that the Qualified Low Income Occupancy has occurred and 100% of the Affordable Residential Units have been leased at least once to qualified low income tenant
| f. | All of the permanent loans have closed and been fully funded (including conversion of the Bond Loan to permanent), or closed and funded concurrently with the payment of the Conversion Installment
| g. | Final completion has been achieved
| h. | LP received Accountant's audited certificate as to the determination of final credit amount and any adjustments top LP Capital Contributions
| i. | Evidence to the LP that prior to or concurrent with the Conversion Installment payment, the principle balance of the MHL Loan has been paid down by $1,000,000 and GP has paid or will pay the portion of the GP capital contribution than due as in Section 4.01a
| j. | At least 7 days prior to Conversion Installation Payment Date, GP has delivered GP Installment Certificate to LP
| k. | All of the following documents have been delivered (Exhibit K)
- Permanent certificate of occupancy
- An as-built SLTA survey
- Evidence of achievement of Qualified Low Income Occupancy
- Evidence that all Reserves have been fully funded
- A certificate from accountants that show: (a) itemized cost of the project; (b) Eligible Housing Creidt Basis; (c) Housing Credit Percentage; (d) setting forth the calculation of any applicable adjustments in LP Capital contribution
- GP representation of Qualified Basis
- Title insurance date down endorsement covering the period from initial installment to conversion installment
- Update on tax counsel opinion
- Updated opinion of legal counsel if any material changes
- Lenders estoppel cert from the lender of the MHL loan dated as of the conversion installment payment date
- Copies of documents in connection with loans not previously delivered to LP
- Evidence of payment of all amounts outstanding under each GC and removal of all liens
- Financial statements of GP and guarantor, dated no earlier than 60 days prior to the Conversion Installment Payment Date
- Evidence that all insurance policies are in full force and effect as of Conversion Installment Payment Date
- Evidence that the Permanent loans at actual interest rate can be serviced by gross revenues
- Evidence of achievement of stabilization
- GP has delivered an executed Property Manager Installment Certificate dated as of conversion Installment Payment Date
- Certificate from architect that punch list items have been completed
- Report from Construction Consultant certifying full completion of punch list items
- Final affidavit from each GC and full and complete releases of lien from each GC including punch list items
- LP has received and executed GC Installment Certificate from each GC, dated as of the Conversion Installment Payment Date; report that all punch list items are complete so that all work necessary for completion of the project and any necessary utilities and roads have been finished and made available for use
- GP has provided LP with certified rent roll showing that as of Conversion Installment Payment Date, at least 270 units are then leased to and occupied by low income tenants and leases are in compliance
Conditions Precedent to Final Installment - May not be paid before April 1, 2012
| a. | All conditions precedent to prior installments have been satisfied
| b. | No default or Event of Default has occurred
| c. | LP has received the 8609
| d. | LP has received Accountant's audited certificate determining final credit amount and any adjustments to LP Cap Contributions
| e. | LP received tax credit compliance audit of 100% of the initial tenant files, prepared by qualifed 3rd party firm
| f. | LP has received estoppel letter from lender of MHL loan, dated not more than 30 days prior to final installment payment date
| g. | LP has received certificate from GP for final Part 3 Historic Application has been filed by GP with Dept of Interior, and evidence to the LP that Dept of Interior has approved
| h. | GP has paid LP amounts under Section 4.02
| i. | Seven days prior to final installment payment date, GP has delivered GP installment certificate to LP
| j. | All of the following documents have been delivered (Exhibit L)
- evidence that housing credits of $1,830,897 per annum have been issued by housing agency
- title insurance date down report covering period through final installment payment date, which discloses no liens or encumberances
- Copies of operating statements and rent rolls, certified as true and correct by GP
- Lenders estoppel cert from lender of MHL loan, dated as of final installment payment date
- If requested by LP, update to the tax counsel opinion on any material tax changes since initial installment
- If requested by LP, update opinion of legal counsel to the partnership, GP or GP affiliate
- If requested by LP, certificate showing (a) itemized costs of the project (b) eligible housing credit basis (c) housing credit percentage (d) qualified rehab expenditures of the project (e) calculation of any applicable adjustments in LP capital contribution
- Filed first year tax return of the partnership, including K1 for LP
- Financial statements of GP, dated no earlier that 60 days prior to final installment payment date
- A compliance audit of all such occpupancies, made by consultant including copies of all initial tenant files
- GP has delivered an executed Property Manager Installment Certificate dated as of conversion Installment Payment Date

## Uptown Refi
15 Year Refi-Uptown Portfolio
M Angelini & A Blakley
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Special Needs (PSH) |  |  | Primary Financing |  | LIHTC - 4%
| Location | Chicago |  |  | Financing - 2nd |  | Bond
| Construction Type | Refinance/ Rehab |  |  | Financing - 3rd |  | Local: City/County Funding
| Number of Units | 449 |  |  | Financing - 4th |  | Local: State Funding
| Population Served | Special Needs (PSH) |  |  | Total Development Costs |  | 43752605
|  | Homeless |  |  | Tax Credit Investor |  | TBD
|  | Dual Diagnosis |  |  | Date Tax Credit Awarded |  | Self Generated at Closing
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 13663550
| Resident Services Type | Case Management - In House |  |  | Total Tax Credit Equity |  | 12297195
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1366355
[5 empty] | Gross Developer Fee |  | 3047000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1523500
[5 empty] | Deferred Developer Fee |  | 1523500
CURRENT STATUS
| Development Stage | Feasibility |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2012-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2013-01-01 |  |  | 2012 Net Developer Fee Forecast |  | 166666.5
| End of Construction | 2014-04-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | 15 Year Refi-Uptown Portfolio
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD | City Council Approval - Mar/Apr 2012
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD | AHP: Atl - May & Jun 2012; Cincy - Apr & Aug 2012; San Fran - Apr & Oct 2012
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2012-12-31 | TBD
| Construction Start | 2013-01-15 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | 15 Year Refi-Uptown Portfolio
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | M Angelini & A Blakley
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | Mar/Apr 2012 | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | 2012-04-30 | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
Due Diligence/Closing Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
Environmental Reports
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
Survey
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
Municipal Review Process
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
Development Team
| Architect/Structural |  |  |  | TBD | TBD
Engineers
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
Architectural
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Design Development
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Construction Drawings
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Historic TC Process
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
Construction Manager/General Contractor
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
Documentation Requirements for Closing Items
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
Standard Agreements
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
Lender 1
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2012-12-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2013-01-15 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Kankakee
Kankakee
L Reyes
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Senior |  |  | Primary Financing |  | LIHTC - 9%
| Location | Kankakee |  |  | Financing - 2nd |  | TBD
| Construction Type | New Construction |  |  | Financing - 3rd |  | TBD
| Number of Units | 70 |  |  | Financing - 4th |  | TBD
| Population Served | Senior |  |  | Total Development Costs |  | 18900000
|  | Senior - Independent |  |  | Tax Credit Investor |  | Enterprise/ Fifth Third
|  | 0 |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 18000156
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 16558343.5044
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1800015.6
[5 empty] | Gross Developer Fee |  | 1743353 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1256980
[5 empty] | Deferred Developer Fee |  | 486373
CURRENT STATUS
| Development Stage | Development |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2013-10-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2013-10-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2014-10-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Kankakee
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-10-01 | TBD
| Construction Start | 2013-10-01 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Kankakee
| LOCATION OF PROJECT: |  |  |  | Kankakee
| LEAD DEVELOPER |  |  |  | L Reyes
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | 2011-12-19 | 2011-12-19
| Preliminary Pro Forma |  |  |  | 2011-12-19 | 2011-12-19
| Proposed Site Control Details |  |  |  | 2011-12-19 | 2011-12-19
| Executed MOU with Seller |  |  |  | 2011-12-09 | 2011-12-15
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | 2011-12-09 | 2011-12-12
Feasibility Period LOC
| LOC setup and modification |  |  |  | 2011-01-03 | 2011-01-03
| Check Requests |  |  |  | on going | on going
| LOC Log |  |  |  | on going | on going
| Cost Coding of all expenses |  |  |  | on going | on going
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | 2011-12-09 | 2011-12-05
| Political Acceptance of Project |  |  |  | 2011-12-09 | 2011-12-05
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | 2011-12-19 | 2011-12-19
| Environmental Issues |  |  |  | 2011-12-19 | 2011-12-15
| Site Construction Issues |  |  |  | 2011-12-14 | 2011-12-14
| Identify Primary Financing Program |  |  |  | 2011-12-19 | 2011-12-19
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | N/A | N/A
| FHLB/AHP |  |  |  | 2012-07-12 | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | 2011-12-15 | TBD
| CHA Financing |  |  |  | N/A | N/A
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | 2011-12-09 | 2011-12-19
| Equity |  |  |  | 2011-12-09 | 2011-12-19
| Subsidy/Gap |  |  |  | 2011-12-09 | 2011-12-19
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | 2011-12-09 | 2011-12-16
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | 2011-12-19 | 2011-12-19
| Environmental Reports |  |  |  | 2011-12-09 | 2011-12-15
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | 2011-12-09 | 2011-12-15
| Phase II |  |  |  | N/A | N/A
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | 2011-12-09 | 2011-11-21
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-10-01 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2013-10-01 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Johnston Ctr 2
Johnston Center 2
D Lyon
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 9%
| Location | Milwaukee |  |  | Financing - 2nd |  | TBD
| Construction Type | New Construction |  |  | Financing - 3rd |  | TBD
| Number of Units | 55 |  |  | Financing - 4th |  | TBD
| Population Served | Family |  |  | Total Development Costs |  | 9625000
|  | Homeless |  |  | Tax Credit Investor |  | TBD
|  | Vets |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | TBD
| Resident Services Type | Case Management - 3rd party |  |  | Total Tax Credit Equity |  | TBD
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | TBD
[5 empty] | Gross Developer Fee |  | 900000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 675000
[5 empty] | Deferred Developer Fee |  | 225000
CURRENT STATUS
| Development Stage | Prospect |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2013-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2014-01-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2015-01-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Johnston Center 2
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-12-31 | TBD
| Construction Start | 2014-01-15 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Johnston Center 2
| LOCATION OF PROJECT: |  |  |  | Milwaukee
| LEAD DEVELOPER |  |  |  | D Lyon
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-12-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2014-01-15 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
[5 empty] | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Danville VA Hospital
Danville VA Hospital Site
D Lyon
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Special Needs (PSH) |  |  | Primary Financing |  | LIHTC - 9%
| Location | Danville |  |  | Financing - 2nd |  | Local: State Funding
| Construction Type | New Construction |  |  | Financing - 3rd |  | Grant Funding - Public or Private
| Number of Units | 65 |  |  | Financing - 4th |  | Grant Funding - Public or Private
| Population Served | Special Needs (PSH) |  |  | Total Development Costs |  | 20000000
|  | Vets |  |  | Tax Credit Investor |  | TBD
|  | Homeless |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 18500000
| Resident Services Type | Case Management - 3rd party |  |  | Total Tax Credit Equity |  | 17279000
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1850000
[5 empty] | Gross Developer Fee |  | 1737500 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1303125
[5 empty] | Deferred Developer Fee |  | 434375
CURRENT STATUS
| Development Stage | Feasibility |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2012-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2013-01-01 |  |  | 2012 Net Developer Fee Forecast |  | 162890.5
| End of Construction | 2013-12-31
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Danville VA Hospital Site
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | 2010-12-31 | 2010-12-31
| Request for Project Approval | 2012-06-12 | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | 2013-01-01 | TBD
| Public Financing Applications | 2013-01-01 | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-12-01 | 2013-12-01
| Construction Start | TBD | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Danville VA Hospital Site
| LOCATION OF PROJECT: |  |  |  | Danville
| LEAD DEVELOPER |  |  |  | D Lyon
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | 2012-02-15 | 2012-02-15
| Photos |  |  |  | 2012-12-31 | TBD
| Preliminary Pro Forma |  |  |  | 2012-12-31 | TBD
| Proposed Site Control Details |  |  |  | 2012-12-31 | TBD
| Executed MOU with Seller |  |  |  | 2012-12-31 | TBD
| Existing Seller Reports |  |  |  | 2012-12-31 | TBD
| Preliminary Site Program |  |  |  | 2012-12-31 | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | 2012-06-12 | TBD
| Check Requests |  |  |  | 2012-06-12 | TBD
| LOC Log |  |  |  | 2012-06-12 | TBD
| Cost Coding of all expenses |  |  |  | 2012-06-12 | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | 2011-12-31 | 2011-12-31
| Political Acceptance of Project |  |  |  | 2011-12-31 | 2011-12-31
| Available Subsidies |  |  |  | 2011-12-31 | 2011-12-31
| Preliminary Neighborhood Scan |  |  |  | 2011-12-31 | 2011-12-31
| Environmental Issues |  |  |  | 2012-06-12 | TBD
| Site Construction Issues |  |  |  | 2012-06-12 | TBD
| Identify Primary Financing Program |  |  |  | 2012-06-12 | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | 2012-06-12 | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | 2012-06-12 | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | 2010-12-31 | 2010-12-31
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | 2012-06-12 | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | N/A | N/A
| 9% LIHTC |  |  |  | 2013-01-01 | TBD
| 4% Bond |  |  |  | N/A | N/A
| TAX CREDIT APPS COMPLETE |  |  |  | 2013-01-01 | TBD
| HUD |  |  |  | N/A | N/A
| HOME/CDBG Funds |  |  |  | N/A | N/A
| Trust Funds |  |  |  | N/A | N/A
| FHLB/AHP |  |  |  | N/A | N/A
| Grants |  |  |  | N/A | N/A
| Operating Subsidy |  |  |  | N/A | N/A
| CHA Financing |  |  |  | N/A | N/A
| PUBLIC FINANCING APPS COMPLETE |  |  |  | 2013-01-01 | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | 2012-06-01 | TBD
| Equity |  |  |  | 2012-06-01 | TBD
| Subsidy/Gap |  |  |  | 2012-06-01 | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | 2011-12-31 | 2011-12-31
| Checklists, Timelines & Updates |  |  |  | 2011-12-31 | 2011-12-31
Due Diligence/Closing Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
Environmental Reports
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
Appraisal
Survey
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
Municipal Review Process
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
Development Team
| Architect/Structural |  |  |  | TBD | TBD
Engineers
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
Architectural
| Timeline |  |  |  | 2012-06-01 | 2012-06-01
| Schematic Design |  |  |  | 2012-06-01 | 2012-06-01
| renderings |  |  |  | 2012-06-01 | 2012-06-01
| drawings |  |  |  | 2012-06-01 | 2012-06-01
Design Development
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Construction Drawings
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
Historic TC Process
| Part I submittal |  |  |  | N/A | N/A
| Part II submittal |  |  |  | N/A | N/A
| NPS approval |  |  |  | N/A | N/A
| Part III Certification submittal |  |  |  | N/A | N/A
Construction Manager/General Contractor
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
Documentation Requirements for Closing Items
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-12-01 | 2013-12-01
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT |  |  |  |  | TBD | TBD
| Construction Construction Start |  |  |  | TBD | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
Site Visits for Monthly Draw Review
| Quarterly Project Coordinating Meetings |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
Dev Fee Installment Payment Conditions
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | N/A | N/A
| Owners Sworn Statement |  |  |  | N/A | N/A
| Invoices |  |  |  | N/A | N/A
| Sources Statement |  |  |  | N/A | N/A
| Escrow Disbursement Statement |  |  |  | N/A | N/A
| Internal Reconciliation |  |  |  | N/A | N/A
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
[5 empty] | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Childrens Memorial
Children's Memorial Site
M Angelini
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Senior |  |  | Primary Financing |  | LIHTC - 9%
| Location | Chicago |  |  | Financing - 2nd |  | TBD
| Construction Type | Adaptive/ Rehab |  |  | Financing - 3rd |  | TBD
| Number of Units | 95 |  |  | Financing - 4th |  | TBD
| Population Served | Senior |  |  | Total Development Costs |  | 17500000
|  | Senior - Independent |  |  | Tax Credit Investor |  | TBD
|  | N/A |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 13125000
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 9450000
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1312500
[5 empty] | Gross Developer Fee |  | 1750000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1312500
[5 empty] | Deferred Developer Fee |  | 437500
CURRENT STATUS
| Development Stage | Prospect |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2013-03-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2013-03-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2014-06-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Children's Memorial Site
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-03-31 | TBD
| Construction Start | 2013-03-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Children's Memorial Site
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | M Angelini
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-03-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2013-03-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Englewood
Englewood Apartments
M Angelini
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Special Needs (PSH) |  |  | Primary Financing |  | LIHTC - 9%
| Location | Chicago |  |  | Financing - 2nd |  | Local: City/County Funding
| Construction Type | New Construction |  |  | Financing - 3rd |  | HOME
| Number of Units | 99 |  |  | Financing - 4th |  | N/A
| Population Served | Special Needs (PSH) |  |  | Total Development Costs |  | 16780500
|  | Homeless |  |  | Tax Credit Investor |  | US Bank
|  | Dual Diagnosis |  |  | Date Tax Credit Awarded |  | 2008
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 12585375
| Resident Services Type | Case Management - In House |  |  | Total Tax Credit Equity |  | 11452691.25
| Funding Source | Government Contracts |  |  | Annual Tax Credit Award |  | 1258537.5
[5 empty] | Gross Developer Fee |  | 1000000 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 360000
[5 empty] | Deferred Developer Fee |  | 640000
CURRENT STATUS
| Development Stage | Operations - Sub Phase Close Out |  |  | Percent Complete |  | 100%
| Date of Deal Close | 2008-12-01 |  |  | Developer Fee Received To Date |  | 360000
| Start of Construction | 2008-12-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2010-09-01
UPCOMING TASKS
- Provided a letter of direction to title company to reimburse MHL from escrow related to vendors who have no liens and are up to date on payment - Dolores will contact Tony when underwriters have reviewed and approved - Duane Morris is working on a letter to title to have title underwriting determine which vendors are fully paid and release money from escrow to MHL VENDORS WITH LIENS: City Cottage - have filed Notice of Attorney's Lien Glass Designers and Spancrete - we are awaiting the results of water testing to be done April 23-27 to see if these vendors still have warranty responsibilties related to water leaks at the property Armstrong -- asking to settle for $82,246-- Midwest believes they are still owed $25,359 - Igal is looking into this Once negotiations are complete, we will use remaining escrow balances coming to MHL to pay MacArthur LOC
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Englewood Apartments
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | Done | Done
| Request for Project Approval | Done | Done
| First Dev Coord Mtg | Done | Done
| Tax Credit Applications | Done | Done
| Public Financing Applications | Done | Done
| Financing Complete | Done | Done
| Due Diligence Complete | Done | Done
| PRC Approval | Done | Done
| Project Set Up in Denver | Done | Done
| Closing | 2008-12-31 | 2008-12-31
| Construction Start | 2008-12-31 | 2008-12-31
| Project Draw Management Set Up | Done | Done
| Project Completion/PIS/C.O. | 2010-09-01 | 2010-09-01
| Cost Cert | Done | Done
| Final Draw | Done | Done | Waiting on final lien waivers to determine the release of escrow balance
| Punch List Complete | In Progress | In Progress | Waiting on the results of water intrusion issues to determine what additional work is required and covered under warranty
| 8609 | In Progress | In Progress
| Turn Over to Asset Mng | In Progress | In Progress
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Englewood Apartments
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | M Angelini
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
Project Set Up Form Completed
Photos
Preliminary Pro Forma
Proposed Site Control Details
Executed MOU with Seller
Existing Seller Reports
Preliminary Site Program
Feasibility Period LOC
LOC setup and modification
Check Requests
LOC Log
Cost Coding of all expenses
Preliminary Municipal/Political Scan
Current Zoning
Political Acceptance of Project
Available Subsidies
Preliminary Neighborhood Scan
Environmental Issues
Site Construction Issues
Identify Primary Financing Program
Preliminary Line of Credit for Feasibility Stage
Detail of Line of Credit needed for Due Diligence/Design
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | Done | Done
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | Done | Done
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | Done | Done
PUBLIC FINANCING APPLICATIONS
Pre Application
9% LIHTC
4% Bond
| TAX CREDIT APPS COMPLETE |  |  |  | Done | Done
HUD
HOME/CDBG Funds
Trust Funds
FHLB/AHP
Grants
Operating Subsidy
CHA Financing
| PUBLIC FINANCING APPS COMPLETE |  |  |  | Done | Done
FINANCING
Detailed Capital Structure
Pro Forma's
Debt
Equity
Subsidy/Gap
Capital Partners (LOI/Commitment Letters)
Debt
i. Letter Of Intent
ii. Commitment Letters
iii. Financial Projections
Equity (NMTC/LIHTC/HTC/ETC)
i. Letter Of Intent
ii. Commitment Letters
iii. Financial Projections
iv. Limited Partnership Agreement
Subsidy/Gap
i. Letter Of Intent
ii. Commitment Letters
| FINANCING COMPLETE |  |  |  | Done | Done
PROJECT DUE DILIGENCE
Photos
Checklists, Timelines & Updates
Due Diligence/Closing Period LOC
LOC setup and modification
Physical/Capital Needs Assessment
Market Study
Environmental Reports
Initial Report
Phase I
Phase II
Appraisal
Survey
Existing
As Built
Municipal Review Process
Zoning
Design
Neighborhood Review/Approval Meetings
Subsidies
TIF
Development Team
Architect/Structural
Engineers
MEP
Energy Modeling/LEEDS/Commissioning
Civil
Construction Manager/General Contractor
Owners Rep
Architectural
Timeline
Schematic Design
renderings
drawings
Design Development
renderings
drawings
Construction Drawings
renderings
drawings
Historic TC Process
Part I submittal
Part II submittal
NPS approval
Part III Certification submittal
Construction Manager/General Contractor
Internal Project Schedule
Cost Estimating
GMP
Contracting
Sustainable Development
Furniture
Relocation
Permit documents
Documentation Requirements for Closing Items
Organizational Documents
LP Formation Documents
GP Formation Documents
JV Formation Documents
Site Control
Standard Agreements
Management
Marketing
| DUE DILIGENCE COMPLETE |  |  |  | Done | Done
2nd PROJECT TEAM COORDINATING MEETING
REQUEST FOR PROJECT APPROVAL |  |  |  |  | Done | Done
Detailed LOC to get through closing
10% Test
PRE CLOSING MEETINGS
Closing Team
Project Specific Closing Checklist
Attorney
Investors
Lender 1
Debt (residential)
Debt (commercial)
Equity (LIHTC/HTC)
Equity (NMTC)
Subsidy/Gap
Lender 0 | Lender 2
Pre Closing Meeting with Denver
Legal
Treasury
Accounting
Compliance
Construction
CLOSING
| Estimated Closing Date |  |  |  | 2008-12-31 | 2008-12-31
POST CLOSING
Post Closing Deliverables
Schedule of Deliverables to Capital Partners
Delivery of Documents to Denver
Set up of Acccounting Items
| PROJECT SETUP IN DENVER |  |  |  | Done | Done
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2008-12-31 | 2008-12-31
Owner's Rep Duties and Contract
| Draw Mng Set Up Prior to Draw 2 |  |  |  | Done | Done
Review of Budget and Schedule
MHI Construction VP Site Visits
Site Visits for Monthly Draw Review
Quarterly Project Coordinating Meetings
Quarterly Dev Coordinating Meetings
Timeline of Major Activities for MSC; RS; AM
Quarterly Dev Coordinating Meetings
Update and Reconcile Activities Timeline
Quarterly Dev Coordinating Meetings
Update and Reconcile Activities Timeline
Quarterly Dev Coordinating Meetings
Update and Reconcile Activities Timeline
Quarterly Dev Coordinating Meetings
Update and Reconcile Activities Timeline
Quarterly Dev Coordinating Meetings
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties
| Certificate of Occupancy/PIS |  |  |  | 2010-09-01 | 2010-09-01
| Cost Certification |  |  |  | Done | Done
Dev Fee Installment Payment Conditions
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM
Owners Sworn Statement | Owners Sworn Statement
Invoices | Invoices
Sources Statement | Sources Statement
Escrow Disbursement Statement | Escrow Disbursement Statement
Internal Reconciliation | Internal Reconciliation
Lender 2 (NMTC)
Detail of Draw Requests from CM
Owners Sworn Statement
Invoices
Sources Statement
Escrow Disbursement Statement
Internal Reconciliation
| FINAL DRAW |  |  |  | Done | Done
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | In Progress | In Progress
Outstanding Items Files
Equity
Historic Part III Certification
Grants
Lease Up Schedule
Document Deliverables
As Built
Warranties
Guarantees
Closeout Manual
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | In Progress | In Progress
| Transfer of Project to Asset Management |  |  |  | In Progress | In Progress
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Menomonee River Valley
Menomonee River Valley
D Lyon
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 9%
| Location | Milwaukee |  |  | Financing - 2nd |  | TBD
| Construction Type | New Construction |  |  | Financing - 3rd |  | TBD
| Number of Units | 60 |  |  | Financing - 4th |  | TBD
| Population Served | Family |  |  | Total Development Costs |  | TBD
|  | Workforce |  |  | Tax Credit Investor |  | TBD
|  | N/A |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | TBD
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | TBD
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | TBD
[5 empty] | Gross Developer Fee |  | TBD | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | TBD
[5 empty] | Deferred Developer Fee |  | TBD
CURRENT STATUS
| Development Stage | Prospect |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2014-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2014-12-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2016-02-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Menomonee River Valley
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2014-12-31 | TBD
| Construction Start | 2014-12-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Menomonee River Valley
| LOCATION OF PROJECT: |  |  |  | Milwaukee
| LEAD DEVELOPER |  |  |  | D Lyon
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2014-12-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2014-12-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Pullman Wheelworks 2
Pullman Wheelworks, Phase 2
M Angelini
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Senior |  |  | Primary Financing |  | LIHTC - 9%
| Location | Chicago |  |  | Financing - 2nd |  | TBD
| Construction Type | New Construction |  |  | Financing - 3rd |  | TBD
| Number of Units | 60 |  |  | Financing - 4th |  | TBD
| Population Served | Senior |  |  | Total Development Costs |  | TBD
|  | Senior - Independent |  |  | Tax Credit Investor |  | TBD
|  | Vets |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | TBD
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | TBD
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | TBD
[5 empty] | Gross Developer Fee |  | TBD | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | TBD
[5 empty] | Deferred Developer Fee |  | TBD
CURRENT STATUS
| Development Stage | Prospect |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2014-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2014-12-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2016-03-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Pullman Wheelworks, Phase 2
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2014-12-31 | TBD
| Construction Start | 2014-12-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Pullman Wheelworks, Phase 2
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | M Angelini
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2014-12-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2014-12-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Danville VA Hospital 2
Danville VA Hospital Site - Phase 2
D Lyon
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Special Needs (PSH) |  |  | Primary Financing |  | LIHTC - 9%
| Location | Danville |  |  | Financing - 2nd |  | Local: State Funding
| Construction Type | New Construction |  |  | Financing - 3rd |  | Grant Funding - Public or Private
| Number of Units | 65 |  |  | Financing - 4th |  | TBD
| Population Served | Special Needs (PSH) |  |  | Total Development Costs |  | 20000000
|  | Homeless |  |  | Tax Credit Investor |  | TBD
|  | Vets |  |  | Date Tax Credit Awarded |  | TBD
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 18500000
| Resident Services Type | Service Coordination |  |  | Total Tax Credit Equity |  | 17279000
| Funding Source | TBD |  |  | Annual Tax Credit Award |  | 1850000
[5 empty] | Gross Developer Fee |  | 1737500 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 1303125
[5 empty] | Deferred Developer Fee |  | 434375
CURRENT STATUS
| Development Stage | Feasibility |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2014-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2015-01-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2015-12-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Danville VA Hospital Site - Phase 2
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2014-12-31 | TBD
| Construction Start | 2014-12-31 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Danville VA Hospital Site - Phase 2
| LOCATION OF PROJECT: |  |  |  | Danville
| LEAD DEVELOPER |  |  |  | D Lyon
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2014-12-31 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2014-12-31 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Westside Resyndication
Westside Resyndication
A Blakley
| DEMOGRAPHICS |  |  |  | FINANCING
| Project Type | Family |  |  | Primary Financing |  | LIHTC - 4%
| Location | Chicago |  |  | Financing - 2nd |  | TBD
| Construction Type | Refinance/ Rehab |  |  | Financing - 3rd |  | TBD
| Number of Units | 315 |  |  | Financing - 4th |  | TBD
| Population Served | Family |  |  | Total Development Costs |  | 30712500
|  | Workforce |  |  | Tax Credit Investor |  | TBD
|  | N/A |  |  | Date Tax Credit Awarded
| Property Mgmt Company | MHMG |  |  | Total Tax Credit Award |  | 9213750
| Resident Services Type | Program - In House |  |  | Total Tax Credit Equity |  | 6633900
| Funding Source | Property Operations |  |  | Annual Tax Credit Award |  | 921375
[5 empty] | Gross Developer Fee |  | 2979112.5 | PLEASE PRINT OUT PAGE AS 2 SIDED
[5 empty] | Net Developer Fee |  | 999999.5
[5 empty] | Deferred Developer Fee |  | 1979113
CURRENT STATUS
| Development Stage | Feasibility |  |  | Percent Complete |  | 0%
| Date of Deal Close | 2013-12-01 |  |  | Developer Fee Received To Date |  | 0
| Start of Construction | 2013-12-01 |  |  | 2012 Net Developer Fee Forecast |  | 0
| End of Construction | 2015-03-01
UPCOMING TASKS
Double click in field to add text to the Upcoming Tasks
Press Alt-Enter to add a line within the field
| SUMMARY OF TASKS AND DEADLINES |  | Westside Resyndication
| Task | Est Complete Date | Actual Complete Date | Additional Detail on Tasks
| Approval to Proceed | TBD | TBD
| Request for Project Approval | TBD | TBD
| First Dev Coord Mtg | TBD | TBD
| Tax Credit Applications | TBD | TBD
| Public Financing Applications | TBD | TBD
| Financing Complete | TBD | TBD
| Due Diligence Complete | TBD | TBD
| PRC Approval | TBD | TBD
| Project Set Up in Denver | TBD | TBD
| Closing | 2013-12-01 | TBD
| Construction Start | 2013-12-01 | TBD
| Project Draw Management Set Up | TBD | TBD
| Project Completion/PIS/C.O. | TBD | TBD
| Cost Cert | TBD | TBD
| Final Draw | TBD | TBD
| Punch List Complete | TBD | TBD
| 8609 | TBD | TBD
| Turn Over to Asset Mng | TBD | TBD
NOTES
OTHER
OTHER
DETAIL OF TASKS AND UPCOMING DEADLINES
| NAME OF PROJECT |  |  |  | Westside Resyndication
| LOCATION OF PROJECT: |  |  |  | Chicago
| LEAD DEVELOPER |  |  |  | A Blakley
| BUSINESS PLAN ACTIVITY |  |  |  | Est. Complete Date | Actual Complete Date
INTIAL PROJECT FEASIBILITY
| Project Set Up Form Completed |  |  |  | TBD | TBD
| Photos |  |  |  | TBD | TBD
| Preliminary Pro Forma |  |  |  | TBD | TBD
| Proposed Site Control Details |  |  |  | TBD | TBD
| Executed MOU with Seller |  |  |  | TBD | TBD
| Existing Seller Reports |  |  |  | TBD | TBD
| Preliminary Site Program |  |  |  | TBD | TBD
Feasibility Period LOC
| LOC setup and modification |  |  |  | TBD | TBD
| Check Requests |  |  |  | TBD | TBD
| LOC Log |  |  |  | TBD | TBD
| Cost Coding of all expenses |  |  |  | TBD | TBD
Preliminary Municipal/Political Scan
| Current Zoning |  |  |  | TBD | TBD
| Political Acceptance of Project |  |  |  | TBD | TBD
| Available Subsidies |  |  |  | TBD | TBD
| Preliminary Neighborhood Scan |  |  |  | TBD | TBD
| Environmental Issues |  |  |  | TBD | TBD
| Site Construction Issues |  |  |  | TBD | TBD
| Identify Primary Financing Program |  |  |  | TBD | TBD
| Preliminary Line of Credit for Feasibility Stage |  |  |  | TBD | TBD
| Detail of Line of Credit needed for Due Diligence/Design |  |  |  | TBD | TBD
| APPROVAL TO PROCEED BY MHL PRESIDENT/SVP |  |  |  | TBD | TBD
REQUEST FOR PROJECT CONCEPT APPROVAL |  |  |  |  | TBD | TBD
1st PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
PUBLIC FINANCING APPLICATIONS
| Pre Application |  |  |  | TBD | TBD
| 9% LIHTC |  |  |  | TBD | TBD
| 4% Bond |  |  |  | TBD | TBD
| TAX CREDIT APPS COMPLETE |  |  |  | TBD | TBD
| HUD |  |  |  | TBD | TBD
| HOME/CDBG Funds |  |  |  | TBD | TBD
| Trust Funds |  |  |  | TBD | TBD
| FHLB/AHP |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Operating Subsidy |  |  |  | TBD | TBD
| CHA Financing |  |  |  | TBD | TBD
| PUBLIC FINANCING APPS COMPLETE |  |  |  | TBD | TBD
FINANCING
Detailed Capital Structure
Pro Forma's
| Debt |  |  |  | TBD | TBD
| Equity |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Capital Partners (LOI/Commitment Letters)
Debt
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
Equity (NMTC/LIHTC/HTC/ETC)
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| iii. Financial Projections |  |  |  | TBD | TBD
| iv. Limited Partnership Agreement |  |  |  | TBD | TBD
Subsidy/Gap
| i. Letter Of Intent |  |  |  | TBD | TBD
| ii. Commitment Letters |  |  |  | TBD | TBD
| FINANCING COMPLETE |  |  |  | TBD | TBD
PROJECT DUE DILIGENCE
| Photos |  |  |  | TBD | TBD
| Checklists, Timelines & Updates |  |  |  | TBD | TBD
| Due Diligence/Closing Period LOC |  |  |  | TBD | TBD
| LOC setup and modification |  |  |  | TBD | TBD
| Physical/Capital Needs Assessment |  |  |  | TBD | TBD
| Market Study |  |  |  | TBD | TBD
| Environmental Reports |  |  |  | TBD | TBD
| Initial Report |  |  |  | TBD | TBD
| Phase I |  |  |  | TBD | TBD
| Phase II |  |  |  | TBD | TBD
| Appraisal |  |  |  | TBD | TBD
| Survey |  |  |  | TBD | TBD
| Existing |  |  |  | TBD | TBD
| As Built |  |  |  | TBD | TBD
| Municipal Review Process |  |  |  | TBD | TBD
| Zoning |  |  |  | TBD | TBD
| Design |  |  |  | TBD | TBD
| Neighborhood Review/Approval Meetings |  |  |  | TBD | TBD
| Subsidies |  |  |  | TBD | TBD
| TIF |  |  |  | TBD | TBD
| Development Team |  |  |  | TBD | TBD
| Architect/Structural |  |  |  | TBD | TBD
| Engineers |  |  |  | TBD | TBD
| MEP |  |  |  | TBD | TBD
| Energy Modeling/LEEDS/Commissioning |  |  |  | TBD | TBD
| Civil |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Owners Rep |  |  |  | TBD | TBD
| Architectural |  |  |  | TBD | TBD
| Timeline |  |  |  | TBD | TBD
| Schematic Design |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Design Development |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Construction Drawings |  |  |  | TBD | TBD
| renderings |  |  |  | TBD | TBD
| drawings |  |  |  | TBD | TBD
| Historic TC Process |  |  |  | TBD | TBD
| Part I submittal |  |  |  | TBD | TBD
| Part II submittal |  |  |  | TBD | TBD
| NPS approval |  |  |  | TBD | TBD
| Part III Certification submittal |  |  |  | TBD | TBD
| Construction Manager/General Contractor |  |  |  | TBD | TBD
| Internal Project Schedule |  |  |  | TBD | TBD
| Cost Estimating |  |  |  | TBD | TBD
| GMP |  |  |  | TBD | TBD
| Contracting |  |  |  | TBD | TBD
| Sustainable Development |  |  |  | TBD | TBD
| Furniture |  |  |  | TBD | TBD
| Relocation |  |  |  | TBD | TBD
| Permit documents |  |  |  | TBD | TBD
| Documentation Requirements for Closing Items |  |  |  | TBD | TBD
| Organizational Documents |  |  |  | TBD | TBD
| LP Formation Documents |  |  |  | TBD | TBD
| GP Formation Documents |  |  |  | TBD | TBD
| JV Formation Documents |  |  |  | TBD | TBD
| Site Control |  |  |  | TBD | TBD
| Standard Agreements |  |  |  | TBD | TBD
| Management |  |  |  | TBD | TBD
| Marketing |  |  |  | TBD | TBD
| DUE DILIGENCE COMPLETE |  |  |  | TBD | TBD
2nd PROJECT TEAM COORDINATING MEETING |  |  |  |  | TBD | TBD
REQUEST FOR PROJECT APPROVAL |  |  |  |  | TBD | TBD
| Detailed LOC to get through closing |  |  |  | TBD | TBD
10% Test |  |  |  |  | TBD | TBD
PRE CLOSING MEETINGS
| Closing Team |  |  |  | TBD | TBD
| Project Specific Closing Checklist |  |  |  | TBD | TBD
| Attorney |  |  |  | TBD | TBD
| Investors |  |  |  | TBD | TBD
| Lender 1 |  |  |  | TBD | TBD
| Debt (residential) |  |  |  | TBD | TBD
| Debt (commercial) |  |  |  | TBD | TBD
| Equity (LIHTC/HTC) |  |  |  | TBD | TBD
| Equity (NMTC) |  |  |  | TBD | TBD
| Subsidy/Gap |  |  |  | TBD | TBD
Lender 0 | Lender 2 |  |  |  | TBD | TBD
Pre Closing Meeting with Denver
| Legal |  |  |  | TBD | TBD
| Treasury |  |  |  | TBD | TBD
| Accounting |  |  |  | TBD | TBD
| Compliance |  |  |  | TBD | TBD
| Construction |  |  |  | TBD | TBD
CLOSING
| Estimated Closing Date |  |  |  | 2013-12-01 | TBD
POST CLOSING
Post Closing Deliverables
| Schedule of Deliverables to Capital Partners |  |  |  | TBD | TBD
| Delivery of Documents to Denver |  |  |  | TBD | TBD
| Set up of Acccounting Items |  |  |  | TBD | TBD
| PROJECT SETUP IN DENVER |  |  |  | TBD | TBD
CONSTRUCTION MANAGEMENT
| Construction Construction Start |  |  |  | 2013-12-01 | TBD
| Owner's Rep Duties and Contract |  |  |  | TBD | TBD
| Draw Mng Set Up Prior to Draw 2 |  |  |  | TBD | TBD
| Review of Budget and Schedule |  |  |  | TBD | TBD
| MHI Construction VP Site Visits |  |  |  | TBD | TBD
| Site Visits for Monthly Draw Review |  |  |  | TBD | TBD
Quarterly Project Coordinating Meetings
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Timeline of Major Activities for MSC; RS; AM |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
| Update and Reconcile Activities Timeline |  |  |  | TBD | TBD
| Quarterly Dev Coordinating Meetings |  |  |  | TBD | TBD
Prepare for MSC to begin PM duties | Prepare for MSC to begin PM duties |  |  |  | TBD | TBD
| Certificate of Occupancy/PIS |  |  |  | TBD | TBD
| Cost Certification |  |  |  | TBD | TBD
| Dev Fee Installment Payment Conditions |  |  |  | TBD | TBD
DRAW MANAGEMENT
Lender 1 (US Bank)
Detail of Draw Requests from CM | Detail of Draw Requests from CM |  |  |  | TBD | TBD
Owners Sworn Statement | Owners Sworn Statement |  |  |  | TBD | TBD
Invoices | Invoices |  |  |  | TBD | TBD
Sources Statement | Sources Statement |  |  |  | TBD | TBD
Escrow Disbursement Statement | Escrow Disbursement Statement |  |  |  | TBD | TBD
Internal Reconciliation | Internal Reconciliation |  |  |  | TBD | TBD
Lender 2 (NMTC)
| Detail of Draw Requests from CM |  |  |  | TBD | TBD
| Owners Sworn Statement |  |  |  | TBD | TBD
| Invoices |  |  |  | TBD | TBD
| Sources Statement |  |  |  | TBD | TBD
| Escrow Disbursement Statement |  |  |  | TBD | TBD
| Internal Reconciliation |  |  |  | TBD | TBD
| FINAL DRAW |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| Punchlist Completion (with MSC and AM) |  |  |  | TBD | TBD
Outstanding Items Files
| Equity |  |  |  | TBD | TBD
| Historic Part III Certification |  |  |  | TBD | TBD
| Grants |  |  |  | TBD | TBD
| Lease Up Schedule |  |  |  | TBD | TBD
| Document Deliverables |  |  |  | TBD | TBD
As Built
| Warranties |  |  |  | TBD | TBD
| Guarantees |  |  |  | TBD | TBD
| Closeout Manual |  |  |  | TBD | TBD
PROJECT CLOSEOUT AND TURNOVER TO ASSET MANAGEMENT
| 8609 Requirements and Completion |  |  |  | TBD | TBD
| Transfer of Project to Asset Management |  |  |  | TBD | TBD
The cells shaded in gray in the Demographics, Financing and Current Status sections are linked to information in the "Detail" worksheet. if you make any changes to the pipeline information, please make those changes in the "Detail" worksheet, not on this sheet.
The information in the cells shaded in gray in the Summary of Tasks and Deadlines section, is linked to the Detail of Tasks and Upcoming Deadlines found just below on this worksheet. You may add additional detail about a task in the cells shaded in white in the Summary of Tasks and Deadlines section.

## Staff Capacity
STAFFING CAPACITY
Key |  |  | Activity | Rating Key | Hours/Month |  | Profile of Avg Developer Summary
Review |  |  | Review | 0.25 | 20 hrs/month |  |  | Target Activity Rate Per Developer | 2.5 | 160 | hrs/month
Feasibility |  |  | Feasibility | 0.25 | 20 hrs/month |  |  | Admin Hours/Month |  | 32 | hrs/month
TC-HUD APP |  |  | TC-HUD APP | 1 | 80 hrs/month |  |  | TOTAL HOURS/MONTH |  | 192 | hrs/month
Pre Dev |  |  | Pre Dev | 1 | 80 hrs/month |  |  | Est. Hours Per Week |  | 47.0204
Closing |  |  | Closing | 1.25 | 100 hrs/month
Const Mng |  |  | Const Mng | 0.5 | 40 hrs/month |  |  | Monthly Avg Hrs Per Developer |  | 203.7551
Conversion |  |  | Conversion | 0.25 | 20 hrs/month |  |  | Monthly Hours @ 40/week x 49 wks |  | 163.3333
8609 |  |  | 8609 | 0.25 | 20 hrs/month
Next Phase |  |  | Next Phase | 0.25 | 20 hrs/month
No Action |  |  | No Action | 0 | 0 hrs/month
Draw Mng |  |  | Draw Mng | 0.25 | 20 hrs/month
Staff Mng |  |  | Staff Mng | 1 | 80 hrs/month
DEVELOPER | Units | 2010 Activity Rating | Stage Q1 2010 | Stage Q2 2010 | Stage Q3 2010 | Stage Q4 2010 | 2011 Activity Rating | Stage Q1 2011 | Stage Q2 2011 | Stage Q3 2011 | Stage Q4 2011
CHICAGO
Galewood SLF | 102 | 0.125 | 8609 | 8609 |  |  | 0
Englewood | 99 | 0.125 | 8609 | 8609 |  |  | 0
Uptown Bond (HWA) | 139 | 0.875 | Closing | Closing | Const Mng | Const Mng | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
Malden Arms | 83 | 1.0625 | TC-HUD APP | TC-HUD APP | Pre Dev | Closing | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
Homan Square (Phase 2) | 195 | 0.0625 | No Action | No Action | No Action | Next Phase | 0.625 | Next Phase | Next Phase | Pre Dev | Pre Dev
Danville VA Hospital Site | 60 | 0.875 | Feasibility | TC-HUD APP | Pre Dev | Closing | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
Keating Building (Phase 1A) | 187 | 1.0625 | TC-HUD APP | TC-HUD APP | Pre Dev | Closing | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
26th & Kostner (Phase 1B) | 60 | 0 | No Action | No Action | No Action | No Action | 0.25 | Next Phase | Next Phase | Next Phase | Next Phase
26th & Kostner | 288 | 0 | No Action | No Action | No Action | No Action | 0.25 | Next Phase | Next Phase | Next Phase | Next Phase
Keating Building | 112 | 0.5 | TC-HUD APP | No Action | No Action | Pre Dev | 1.0625 | Pre Dev | Pre Dev | Pre Dev | Closing
#REF! | #REF! | 0 | No Action | No Action | No Action | No Action | 0.4375 | Next Phase | Next Phase | Next Phase | Pre Dev
TOTAL | #REF! | 4.6875 |  |  |  |  | 4.625
Per Develper Rating |  | 2.3438 |  |  |  |  | 2.3125
Est Hours/Month |  | 203.125 |  |  |  |  | 200.4167
Staffing Required |  | 1.875 |  |  |  |  | 1.85
Staff Allocated |  | 2 |  |  |  |  | 2
Excess/(Under) Capacity |  | 6.25% |  |  |  |  | 7.5%
MILWAUKEE
Roseland Place | 60 | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng | 0.1875 | Conversion | Conversion | 8609
Greenwich Park Apartments | 55 | 0.625 | Feasibility | Feasibility | Pre Dev | Pre Dev | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing
YMCA Austin | 160 | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
MSR 5th Ward Project | 55 | 0.375 | Feasibility | No Action | Feasibility | Pre Dev | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing
Prince Hall (Phase 1) | 55 | 0.0625 | No Action | Review | No Action | No Action | 0.0625 | Feasibility | No Action | No Action | No Action
Library Mall | 55 | 0.0625 | Review | No Action | No Action | No Action | 0.8125 | Feasibility | Pre Dev | Pre Dev | Pre Dev
TOTAL | 440 | 2.6875 |  |  |  |  | 3.6875
Est Hours/Month |  | 116.4583 |  |  |  |  | 159.7917
Staffing Required |  | 1.075 |  |  |  |  | 1.475
Staff Allocated |  | 1 |  |  |  |  | 1
Excess/(Under) Capacity |  | -7.5% |  |  |  |  | -47.5%
CHICAGO METRO SUBURBS
Johnston Center | 91 | 0.4375 | Const Mng | Const Mng | Const Mng | Conversion | 0.125 | 8609 | 8609
Copley Site (Phase 1) | 60 | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
Copley Site | 135 | 0 | No Action | No Action | No Action | No Action | 0.625 | Next Phase | Next Phase | Pre Dev | Pre Dev
Streeterville (Childrens Memorial) | 95 | 0.375 | No Action | Feasibility | Feasibility | Pre Dev | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing
Danville VA Hospital Site/phase1 | 40 | 0.625 | Feasibility | Feasibility | TC-HUD APP | Pre Dev | 0.9375 | Pre Dev | Pre Dev | Closing | Const Mng
Danville (Phase 2) | 50 | 0 | No Action | No Action | No Action | No Action | 0.25 | Next Phase | Next Phase | Next Phase | Next Phase
TOTAL | 471 | 2.5 |  |  |  |  | 3.5
Est Hours/Month |  | 108.3333 |  |  |  |  | 151.6667
Staffing Required |  | 1 |  |  |  |  | 1.4
Staff Allocated |  | 1 |  |  |  |  | 1
Excess/(Under) Capacity |  | 0% |  |  |  |  | -40%
CONSULTANT
Kankakee | 70 | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
Uptown Resyndication | 529 | 0.4375 | Feasibility | Feasibility | Feasibility | Pre Dev | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing
Apartment Acquisitions |  | 0.4375 | No Action | Review | Closing | Review
TOTAL | 599 | 1.9375 |  |  |  |  | 1.5625
Est Hours/Month |  | 83.9583 |  |  |  |  | 67.7083
Staffing Required |  | 0.775 |  |  |  |  | 0.625
Staff Allocated |  | 1 |  |  |  |  | 1
Excess/(Under) Capacity |  | 22.5% |  |  |  |  | 37.5%
ASSET MANAGEMENT
Pullman Wheelworks | 210 | 0.5625 | Feasibility | No Action | Pre Dev | Pre Dev | 0.8125 | TC-HUD APP | Closing | Const Mng | Const Mng
#REF! | #REF! | 0 | No Action | No Action | No Action | No Action | 0 | No Action | No Action | No Action | No Action
West Side Refinance | 315 | 0.875 | Feasibility | Pre Dev | TC-HUD APP | Closing | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
TOTAL | #REF! | 1.4375 |  |  |  |  | 1.3125
Est Hours/Month |  | 62.2917 |  |  |  |  | 56.875
Staffing Required |  | 0.575 |  |  |  |  | 0.525
Staff Allocated |  | 0.575 |  |  |  |  | 0.525
Excess/(Under) Capacity |  | 0% |  |  |  |  | 0%
DRAW MANAGEMENT
Countryside Senior Apts | 0 | 0.125 | Draw Mng | Draw Mng | No Action | No Action | 0 | No Action | No Action | No Action | No Action
Johnston Center | 0 | 0.1875 | Draw Mng | Draw Mng | Draw Mng | No Action | 0 | No Action | No Action | No Action | No Action
Roseland Place | 0 | 0.25 | Draw Mng | Draw Mng | Draw Mng | Draw Mng | 0 | No Action | No Action | No Action | No Action
Roseland Place | 60 | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng | 0.3125 | Const Mng | Conversion | Conversion | Conversion
Uptown Bond (HWA) | 0 | 0.1875 | No Action | Draw Mng | Draw Mng | Draw Mng | 0.25 | Draw Mng | Draw Mng | Draw Mng | Draw Mng
Malden Arms | 0 | 0.0625 | No Action | No Action | No Action | Draw Mng | 0.25 | Draw Mng | Draw Mng | Draw Mng | Draw Mng
Keating Building (Phase 1A) | 0 | 0.0625 | No Action | No Action | No Action | Draw Mng | 0.25 | Draw Mng | Draw Mng | Draw Mng | Draw Mng
Greenwich Park Apartments | 0 | 0 | No Action | No Action | No Action | No Action | 0.0625 | No Action | No Action | No Action | Draw Mng
YMCA Austin | 0 | 0.0625 | No Action | No Action | No Action | Draw Mng | 0.25 | Draw Mng | Draw Mng | Draw Mng | Draw Mng
Copley Site (Phase 1) | 0 | 0.0625 | No Action | No Action | No Action | Draw Mng | 0.25 | Draw Mng | Draw Mng | Draw Mng | Draw Mng
TOTAL | 60 | 1.5 |  |  |  |  | 1.625
Est Hours/Month |  | 65 |  |  |  |  | 70.4167
Staffing Required |  | 0.6 |  |  |  |  | 0.65
Staff Allocated |  | 1 |  |  |  |  | 1
Excess/(Under) Capacity |  | 40% |  |  |  |  | 35%
FERGUS
Countryside Senior Apts | 70 | 0.375 | Const Mng | Const Mng | Conversion | 8609 | 0.125 | 8609 | 8609 | No Action | No Action
Uptown Bond (HWA) | 0 | 0.625 | Closing | Closing | No Action | No Action | 0 | No Action | No Action | No Action | No Action
MHL-NNCHC ILF | 80 | 0.625 | Feasibility | Feasibility | Pre Dev | Pre Dev | 1.0625 | TC-HUD APP | Pre Dev | Pre Dev | Closing
Acquistion Private Equity Fund |  | 0.8125 | Feasibility | Pre Dev | Pre Dev | Pre Dev | 1 | Pre Dev | Pre Dev | Pre Dev | Pre Dev
Expansion to Other Geographic Areas |  | 0.25 | Feasibility | Feasibility | Feasibility | Feasibility | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
Regional 4% Fund for NSP |  | 0.25 | Feasibility | Feasibility | Feasibility | Feasibility | 0.5 | Const Mng | Const Mng | Const Mng | Const Mng
Staff Management |  | 1 | Staff Mng | Staff Mng | Staff Mng | Staff Mng | 1 | Staff Mng | Staff Mng | Staff Mng | Staff Mng
TOTAL | 150 | 3.9375 |  |  |  |  | 4.1875
Est Hours/Month |  | 170.625 |  |  |  |  | 181.4583
Staffing Required |  | 1.575 |  |  |  |  | 1.675
Staff Allocated |  | 1.4 |  |  |  |  | 1.35
Excess/(Under) Capacity |  | -12.5% |  |  |  |  | -24.07%
TOTAL UNITS | #REF!
TOTAL |  | 18.6875 |  |  |  |  | 20.5
Est Hours/Month |  | 809.7917 |  |  |  |  | 888.3333
Staffing Required |  | 7.475 |  |  |  |  | 8.2
Staff Allocated |  | 7.975 |  |  |  |  | 7.875
Excess/(Under) Capacity |  | 6.27% |  |  |  |  | -4.127%

## Debt Repay Schedule
Updated: 3-14-12 |  | Principle Balance 12/31/11 | Obligation as of 12/31/11 | 2012 Running Obligation | 2012 Revenue Source/ Strategy | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | Project Balance
PREDEVELOPMENT LOC
ALLSTATE LINE OF CREDIT |  | 875000 |  | 725000 |  | 575000 | 425000 | 0
$1M due in 2015
| Firethorne |  | 11153 | 0 | Unbudgeted revenue from Denis Pierce, 180 Properties and Roseland - PAID DOWN MARCH 2012 | [6 empty] | 0
| Danville Senior Campus |  | 55634 | 56470 | Grayslake would need to be significantly reduced this year to make room for this project or it needs to be rolled into an MHI line | [6 empty] | 56470
| Grayslake SLF Apartments |  | 565512 | 569013 | Need strategy and timing to pay this down | [6 empty] | 569013
| Kane County NSP |  | 118103 | 114194 | Unbudgeted revenue from Denis Pierce, 180 Properties and Roseland | [6 empty] | 114194
| Copley Redevelopment |  | 93145 | 94545 | Unbudgeted revenue from Denis Pierce, 180 Properties and Roseland | [6 empty] | 94545
| TOTAL OBLIGATION |  | 843547 | 834222 |  | 0 | 0 | 0 | 0 | 0 | 0
| LOC RUNNING BALANCE |  | 843547 | 1677769 |  | 1677769 | 1677769 | 1677769 | 1677769 | 1677769 | 1677769 | 834222
MACARTHUR LINE OF CREDIT |  | 1750000 | 1750000 | 1750000 |  | 1750000 | 1750000 | 1750000 | 1750000 | 1750000 | 0
$1.75 due in 2018
| Englewood - Developer Fee |  | 258442 | 258442 | To be paid down with developer fees - need to determine if we pay down MHL LOC or MacArthur first, using available cash; does not appear to have enough cash to pay both down | [6 empty] | 258442
| Englewood - Development |  | 298243.75 | 298244 | The source will be the property itself – we will renegotiate with IHDA as we had stated once we determined the amount of our liability. We will suspend payments on their cash flow payments until we are repaid, and then reinstate them. | [6 empty] | 298244
| Harold Washington - Construction |  | 228547 | 195346 | Open during construction - to be paid down using funds from the 850 operating account | [6 empty] | 195346
| 850 Eastwood - Construction |  | 202327.98 | 205010 | Open during construction - to be paid down at construction close | [6 empty] | 205010
| Countryside - Developer Fee |  | 64907 | 64907 | To be paid off at receipt of final developer fee in 2012 | [6 empty] | 64907
| HWA-850 Eastwood Developer Fee |  | 250000 | 250000 | To be paid down with deffered developer fees | -62500 | -62500 | -62500 | -62500 |  |  | 0
| Aurora/Galena |  | 648.44 | 656 | [7 empty] | 656
| Uptown Portfolio |  | 0 | 0
| Harold Washington - Operating |  | 244276.75 | 245310 | [7 empty] | 245310
| Malden Arms II - Operating |  | 35713.89 | 36320 | Analyzing monthly cash flow; putting together a schedule of paydown and if cash flow is the source of the paydown | [6 empty] | 36320
| Belray |  | 16329.1905 | 16525 | Pay off at resyndication in Dec 2012 | [6 empty] | 16525
| Delmar |  | 38024 | 38480 | Pay off at resyndication in Dec 2012 | [6 empty] | 38480
| Major Jenkins |  | 37323.482 | 37722 | Pay off at in APRIL 2012 because we now have control of reserves | [6 empty] | 37722
| TOTAL OBLIGATION |  | 1674783.4826 | 1646962 |  | -62500 | -62500 | -62500 | -62500 | 0 | 0
| LOC RUNNING BALANCE |  | 1674783.4826 | 3321745.4826 |  | 3259245.4826 | 3196745.4826 | 3134245.4826 | 3071745.4826 | 3071745.4826 | 3071745.4826 | 1396962
MHI LINE OF CREDIT - CHASE
| 26th & Kostner (Keating Bldg) |  | 266396 | 269530 | To be paid down in December 2012 at close | [6 empty] | 269530
| Kankakee |  | 8601 | 34415 | Architect for $15k (expecting $15k from Enterprise) | [6 empty] | 34415
| Grayslake Senior Housing |  | 30104 | 16032 | [7 empty] | 16032
| Milwaukee 5th Ward Senior Housing |  | 82188 | 83155 | Rescoping the deal to make it work under 4%; new numbers upcoming | [6 empty] | 83155
| Milwaukee East Side Workforce Housing |  | 153147 | 154948 | Rescoping the deal to make it work under 4%; new numbers upcoming | [6 empty] | 154948
| Division & Clybourn (Near North 2) |  | 31248 | 31797 | Budgeted to write down in APRIL 2012 | [6 empty] | 31797
| Sterling Park Apartments |  | 830863 | 952710 | To be paid down in July 2012 at close | [6 empty] | 952710
| TOTAL OBLIGATION |  | 1402547 | 1542587 |  | 0 | 0 | 0 | 0 | 0 | 0
| LOC RUNNING BALANCE |  | 1402547 | 2945134 |  | 2945134 | 2945134 | 2945134 | 2945134 | 2945134 | 2945134 | 1542587
MHI LINE OF CREDIT - MACARTHUR
| Austin YMCA Redevelopment |  | 21293.22 | 21506 | [7 empty] | 21506
| Pullman Wheelworks |  | 713397.46 | 270030 | The majority paid down in January. There was an expense incurred in February which was a timing draw which should be repaid right away out of the next draw. | [6 empty] | 270030
| TOTAL OBLIGATION |  | 734690.68 | 291536 |  | 0 | 0 | 0 | 0 | 0 | 0
| LOC RUNNING BALANCE |  | 734690.68 | 1026226.68 |  | 1026226.68 | 1026226.68 | 1026226.68 | 1026226.68 | 1026226.68 | 1026226.68 | 291536
DEVELOPMENT LOC
MHI LINE OF CREDIT - CHASE
| Englewood Apartments |  | 444089 | 447271 | To be repaid from escrow; doing a reconciliation of the escrow balance sheet | [6 empty] | 447271
| 850 Eastwood |  | 48394 | 50755 | Talk to Gary and see where this is coming from; should this be closed? Bobby has talked with Gary will pay through a draw | [6 empty] | 50755
| Countryside Senior Apartments |  | 33675 | 7987 | All building operations - fronted to the property; strategy for payback needs to be determined | [6 empty] | 7987
| Johnston Center |  | 52727 | 52727 | Run the G/L -- determine what the costs are and work on a strategy repayment | [6 empty] | 52727
| Harold Washington |  | 26660 | 27539 | Talk to Gary and see where this is coming from; should this be closed? Bobby has talked with Gary will pay through a draw | [6 empty] | 27539
| Grayslake |  | 2837 | 0 | [7 empty] | 0
| TOTAL OBLIGATION |  | 608382 | 586279 |  | 0 | 0 | 0 | 0 | 0 | 0
| LOC RUNNING BALANCE |  | 608382 | 1194661 |  | 1194661 | 1194661 | 1194661 | 1194661 | 1194661 | 1194661 | 586279
OPERATING LOC
MHI LINE OF CREDIT - CHASE
| Parkside Terraces |  | 68279.77 | 69195 | [7 empty] | 69195
| Wentworth Commons |  | 66276.52 | 67089 | [7 empty] | 67089
| Holland Apartments |  | 2597.59 | 2598 | [7 empty] | 2598
| Malden Arms |  | 240.11 | 476 | [7 empty] | 476
| TOTAL OBLIGATION |  | 137393.99 | 139358 |  | 0 | 0 | 0 | 0 | 0 | 0
| LOC RUNNING BALANCE |  | 137393.99 | 276751.99 |  | 276751.99 | 276751.99 | 276751.99 | 276751.99 | 276751.99 | 276751.99 | 139358
Note on B36: gellefson: aka mercy senior residences
Note on B37: gellefson: aka greenwich park apts

## 2012 Detail by Month
|  | Principle Balance 12/31/11 | Approved Line | Obligation as of 12/31/11 | Jan |  | Feb |  | Mar |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL | BALANCE
PREDEVELOPMENT LOC
XXX LINE OF CREDIT |  | 875000
$1M due in 2015
| Firethorne |  |  | 11153 | 11210 | 57 | 11263 | 53 | 0 | -11263 | [9 empty] | 0 | 11153
| Danville Senior Campus |  | 55250 | 55634 | 55918 | 284 | 56184 | 266 | 56470 | 286 | [9 empty] | 56470 | 112104
| Grayslake SLF Apartments |  | 578000 | 565512 | 568402 | 2890 | 566090 | -2312 | 569013 | 2923 | [9 empty] | 569013 | 1134525
| Kane County NSP |  | 100000 | 118103 | 110131 | -7972 | 111670 | 1539 | 114194 | 2524 | [9 empty] | 114194 | 232297
| Copley Redevelopment |  | 108000 | 93145 | 93620 | 475 | 94066 | 446 | 94545 | 479 | [9 empty] | 94545 | 187690
| TOTAL OBLIGATION |  |  | 843547 | 839281 |  | 839273 |  | 834222 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834222 | 1677769
| Variance from Total Principle |  |  | 843547 | 35719 |  | 35727 |  | 869949 |  | 869949 | 869949 | 869949 | 869949 | 869949 | 869949 | 869949 | 869949 | 869949 | 1677769
M LINE OF CREDIT |  | 1750000 |  | 1750000
$1.75 due in 2018
| Englewood - Developer Fee |  | 258442 | 258442 | 258442 | 0 | 258442 | 0 | 258442 | 0 | [9 empty] | 258442 | 516884
| Englewood - Development |  | 298244 | 298243.75 | 298244 | 0.25 | 298244 | 0 | 298244 | 0 | [9 empty] | 298244 | 596487.75
| Harold Washington - Construction |  | 100000 | 228547 | 228871 | 324 | 195020 | -33851 | 195346 | 326 |  |  |  | -195020 | [5 empty] | 195346 | 423893
| 850 Eastwood - Construction |  | 225000 | 202327.98 | 203671 | 1343.02 | 204552 | 881 | 205010 | 458 |  |  |  | -204552 | [5 empty] | 205010 | 407337.98
| Countryside - Developer Fee |  | 64907 | 64907 | 64907 | 0 | 64907 | 0 | 64907 | 0 | -64907 | [8 empty] | 64907 | 129814
| HWA-850 Eastwood Developer Fee |  | 250000 | 250000 | 250000 | 0 | 250000 | 0 | 250000 | 0 | [9 empty] | 250000 | 500000
| Aurora/Galena |  | 50833 | 648.44 | 651 | 2.56 | 653 | 2 | 656 | 3 | [9 empty] | 656 | 1304.44
| Uptown Portfolio |  | 110000 | 0 |  |  |  |  | 0 | 0
| Harold Washington - Operating |  | 285000 | 244276.75 | 245310 | 1033.25 | 245310 | 0 | 245310 | 0 | [9 empty] | 245310 | 489586.75
| Malden Arms II - Operating |  | 50000 | 35713.89 | 35919 | 205.11 | 36112 | 193 | 36320 | 208 |  |  |  |  | -36112 |  |  |  |  | 36320 | 72033.89
| Belray |  | 14799 | 16329.1905 | 16396 | 66.8095 | 16458 | 62 | 16525 | 67 | [8 empty] | -16458 | 16525 | 32854.1905
| Delmar |  | 34361 | 38024 | 38179 | 155 | 38324 | 145 | 38480 | 156 | [8 empty] | -38324 | 38480 | 76504
| Major Jenkins |  | 33826 | 37323.482 | 37476 | 152.518 | 37618 | 142 | 37722 | 104 | -37722 | [8 empty] | 37722 | 75045.482
| TOTAL OBLIGATION |  |  | 1674783.4826 | 1678066 |  | 1645640 |  | 1646962 |  | -102629 | 0 | 0 | -399572 | -36112 | 0 | 0 | 0 | -54782 | 1646962
| LOC RUNNING BALANCE |  |  | 1674783.4826 | 71934 |  | 104360 |  | 1751322 |  | 1648693 | 1648693 | 1648693 | 1249121 | 1213009 | 1213009 | 1213009 | 1213009 | 1158227 | 3321745.4826
INTERNAL LINE OF CREDIT
| 26th & Kostner (Keating Bldg) |  | 263000 | 266396 | 267459 | 1063 | 268458 | 999 | 269530 | 1072 | [6 empty] | -268458 |  |  | 269530 | 535926
| Kankakee |  | 50000 | 8601 | 15142 | 6541 | 37521 | 22379 | 34415 | -3106 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | 62500 | -537521 | 34415 | 43016
| Grayslake Senior Housing |  | 525000 | 30104 | 15904 | -14200 | 15966 | 62 | 16032 | 66 | [9 empty] | 16032 | 46136
| Milwaukee 5th Ward Senior Housing |  | 122000 | 82188 | 82516 | 328 | 82824 | 308 | 83155 | 331 | [9 empty] | 83155 | 165343
| Milwaukee East Side Workforce Housing |  | 165812 | 153147 | 153758 | 611 | 154332 | 574 | 154948 | 616 | [9 empty] | 154948 | 308095
| Division & Clybourn (Near North 2) |  | 33231 | 31248 | 31553 | 305 | 31671 | 118 | 31797 | 126 | -31797 | [8 empty] | 31797 | 63045
| Sterling Park Apartments |  | 953125 | 830863 | 843446 | 12583 | 924091 | 80645 | 952710 | 28619 | [7 empty] | -924091 |  | 952710 | 1783573
| TOTAL OBLIGATION |  |  | 1402547 | 1409778 |  | 1514863 |  | 1542587 |  | 30703 | 62500 | 62500 | 62500 | 62500 | 62500 | -205958 | -861591 | -537521 | 1542587
MHI LINE OF CREDIT
| Austin YMCA Redevelopment |  | 50000 | 21293.22 | 21366 | 72.78 | 21433 | 67 | 21506 | 73 | [9 empty] | 21506 | 42799.22
| Pullman Wheelworks |  | 592468 | 713397.46 | 79714 | -633683.46 | 211997 | 132283 | 270030 | 58033 | [9 empty] | 270030 | 983427.46
| TOTAL OBLIGATION |  |  | 734690.68 | 101080 |  | 233430 |  | 291536 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291536
DEVELOPMENT LOC
MHI LINE OF CREDIT - XXX BANK
| Englewood Apartments |  | 2071600 | 444089 | 445169 | 1080 | 446183 | 1014 | 447271 | 1088 | [9 empty] | 447271 | 891360
| 850 Eastwood |  | 450000 | 48394 | 47615 | -779 | 50699 | 3084 | 50755 | 56 | [9 empty] | 50755 | 99149
| Countryside Senior Apartments |  | 70000 | 33675 | 7923 | -25752 | 7954 | 31 | 7987 | 33 | [9 empty] | 7987 | 41662
| Johnston Center |  | 51000 | 52727 | 52727 | 0 | 52727 | 0 | 52727 | 0 | [9 empty] | 52727 | 105454
| Harold Washington |  | 0 | 26660 | 26660 | 0 | 27539 | 879 | 27539 | 0 | [9 empty] | 27539 | 54199
| Grayslake |  | 0 | 2837 | 0 | -2837 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 2837
| TOTAL OBLIGATION |  |  | 608382 | 580094 |  | 585102 |  | 586279 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 586279
OPERATING LOC
LINE OF CREDIT - BANK
| Parkside Terraces |  | 150000 | 68279.77 | 71378 | 3098.23 | 71674 | 296 | 69195 | -2479 | [9 empty] | 69195 | 137474.77
| Wentworth Commons |  | 145000 | 66276.52 | 66552 | 275.48 | 66881 | 329 | 67089 | 208 | [9 empty] | 67089 | 133365.52
| Holland Apartments |  | 41500 | 2597.59 | 2598 | 0.41 | 2598 | 0 | 2598 | 0 | [9 empty] | 2598 | 5195.59
| Malden Arms |  | 53000 | 240.11 | 320 | 79.89 | 395 | 75 | 476 | 81 | [9 empty] | 476 | 716.11
| TOTAL OBLIGATION |  |  | 137393.99 | 140848 |  | 141548 |  | 139358 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139358
| LOC RUNNING BALANCE |  |  | 137393.99 | 278241.99 |  | 419789.99 |  | 559147.99 |  | 559147.99 | 559147.99 | 559147.99 | 559147.99 | 559147.99 | 559147.99 | 559147.99 | 559147.99 | 559147.99 | 276751.99
Note on J5: tmastracci: Paydown occurred in March
Note on B35: gellefson: aka mercy senior residences
Note on B36: gellefson: aka greenwich park apts